## Read Me
Evidence Register: Brownfield to Repo 2.0 (logistics shipment, fleet, routing ops)
Delta-Team, AI-FDE Sprint 3. As of 2026-10-08. Built from the repository by deliverables/_build/build_workbook.py.
How to use this workbook
Start on Dashboard for the headline numbers. Every other sheet is the detail behind one tile.
Each evidence row links to the file on GitHub (private repository; sign in to open). SHA-256 lets anyone check the file is unchanged.
Filters are on every table. Green = done, amber = partial or changed, red = not met, blocked or deferred.
Sheets
Dashboard: headline numbers, all computed by formula from the sheets below.
Repo 1.0 vs 2.0: capability by capability, what was delivered and what exists now, with findings and evidence.
File Inventory: files and code lines per area, delivered commit 698e858 vs current main.
Evidence Register: all 146 hash-registered evidence files, with stage, findings addressed, rubric criteria and link.
Findings: the 62 baseline findings with severity, final disposition and rubric criteria.
Red Team: the 12 attacks run against the delivered code and against Repo 2.0.
KPIs: K1 to K10 before and after, with the honest reading.
Rubric Coverage: per criterion summary and the 119 file-level matrix rows.
Go-No-Go: the 12 readiness gates and their state today.
Decisions: the 23 open questions and the operator's decision on each (Runbook 04).
Risks: residual risks; none is accepted by a named person.
Journey: the 20 stages (A to T) in six phases, with the commit that recorded them.
Semantic Layer: every file in semantic-layer/ with its format and role.
Evidence tags used in the source documents
[VF] verified fact, read in a cited file [INF] inference [ASM] assumption [UNK] unknown
Limits stated up front
No real AI model was called; all AI evidence uses the deterministic provider. Nothing is deployed. No business KPI moved; K1 to K8 are computed from a static synthetic fixture. One operator plus one agent built, tested and graded the work: no independent review.

## Dashboard
Dashboard: Repo 1.0 → Repo 2.0, in numbers
Every value below is a formula over the detail sheets. As of 2026-10-08.
Evidence
Hash-registered evidence files | 146
Files touching R1 | 30
Files touching R2 | 73
Files touching R3 | 20
Files touching R4 | 20
Files touching R5 | 39
Findings
Baseline findings | 62
Severity S1 | 25
FIXED | 43
FIXED-IN-TREE | 4
PARTIAL | 10
CHANGED | 2
DEFERRED | 2
ACCEPTED-PROPOSED | 1
Proof
Attacks that succeed on Repo 1.0 (of 12) | 10
Attacks that succeed on Repo 2.0 (of 12) | 0
Readiness gates passed (of 12) | 6
Readiness gates failed | 5
Tracked files in the application folder, 1.0 → 2.0 | 51 → 158
Governance
Open questions decided or ratified | 22
Open questions deferred | 1
Rubric sub-dimensions | 36
Sub-dimensions MET | 24
Sub-dimensions NOT MET or BLOCKED | 3
Risk acceptances signed by a named person | 0 | Input: 0 of 12 (docs/25-governance/risk-acceptance-register.md)

## Repo 1.0 vs 2.0
Repo 1.0 (as delivered) vs Repo 2.0 (as built)
Repo 1.0 = commit 698e858 (delivered bytes). Repo 2.0 = main today. Status is the agent's reading of the finding dispositions; see Findings.
Area | Repo 1.0 (as delivered) | Repo 2.0 (as built) | Status | Findings | Evidence
Version control and quick-start | Not under version control; documented test command fails (exit 2, missing httpx); run command wrong | Git with baseline tags; quick-start works; 181 passed, 1 skipped, 7 expected xfail | Fixed | F-01, F-02, F-03 | evidence/07-repo-assessment/EVD-C-02-quickstart-transcript.txt; evidence/15-modernization/EVD-H-02-quickstart-after.txt
Tests and coverage | 3 tests (0 collected without httpx); coverage 45% | 181 tests plus 7 characterisation tests that pin old behaviour; 97% coverage (apps and etl) | Fixed | F-51 | evidence/34-after-kpis/EVD-O-01-after-kpis.json
Dependencies and supply chain | Versions pinned but no lockfile or hashes; no SBOM | Hash-pinned lockfiles; SBOM (runtime 21, dev 58 components); 0 known vulnerabilities | Fixed | F-04, F-49 | evidence/27-hardening/EVD-M-01-pip-audit-runtime.json
Identity | Role read from a client-supplied X-User-Role header | Signed bearer token (HS256, alg none rejected); JWKS verifier is a fail-closed stub; no identity provider | Fixed (interim scheme) | F-17 | evidence/26-tevv/EVD-L-03-redteam-v2.json (RT-02, RT-11)
Authorisation | Flat five-role allow-list including a persona from another domain; Rego file used by no code | Deny-by-default policy engine driven by access-semantics.yaml (persona x entity x purpose, field mask or drop); Rego generated from it and tested in CI; scope narrowing declared but not enforced | Fixed (scope partial) | F-18, F-19, F-21 | evidence/26-tevv/EVD-L-03-redteam-v2.json (RT-03)
Record lookup | Scans every column; a miss returns the wrong record; REC-0001 key collides across entities | Identifier must match the entity key pattern (422); a miss is 404 and audited; colliding rows quarantined | Fixed | F-30, F-31, F-32 | evidence/26-tevv/EVD-L-03-redteam-v2.json (RT-04 to RT-06)
AI endpoint | No authorisation; guardrail_status not_enforced; no output schema; str.format on untrusted text; output echoes the first column | Authorised and rate-limited; allow-listed, sanitised context; schema and leak checks; fallback then abstain; suggest-only. Deterministic provider only | Fixed (no real model) | F-20, F-22, F-23, F-24, F-25, F-29 | evidence/26-tevv/EVD-L-02-final-eval-run.json; EVD-L-03 RT-01, RT-07 to RT-09, RT-12
Human approval | None | Every suggestion registered; approve or reject once (409 on repeat); requester may approve their own (RA-04) | Fixed (no four-eyes) | F-26 | evidence/26-tevv/EVD-L-03-redteam-v2.json (RT-10)
Model provenance and tokens | Model id is a constant; token count fabricated | Model, version, prompt version and config hash on every answer; token count labelled as an estimate | Partial | F-27, F-28 | docs/final-prd/final-ai-agent-baseline.md
Audit | Records time, action, details only; naive timestamps; local file | Hash-chained events with actor, correlation id, tenant, resource and policy decision; verify endpoint; tampering detected; still a local file sink | Partial | F-43, F-44, F-45 | evidence/31-observability/EVD-N-02-reconstruction.json
Data quality | Duplicates, blank rows, impossible timestamps, polluted categories; ETL counts defects and discards them | ETL validates with the API's rules; bad rows quarantined with a run id; curated layer; raw fixture left byte-identical | Fixed | F-33 to F-41, F-58, F-61, F-62 | evidence/11-data-context/EVD-D-02-enum-violations.csv
Semantic layer | None | v2.0: 8 YAML definition files, JSON Schema, API contract, generated JSON, 23 layer tests and 5 conformance tests | Fixed | F-37 | evidence/11-data-context/EVD-D-06-semantic-layer-v2-hashes.json
Observability | Notes only; a third of events cannot be correlated | Correlation id on every request; /metrics; KPI endpoint; no tracing, no collector, no alert recipients | Partial | F-42, F-46 | docs/31-observability
CI and change control | CI runs pytest only and had never run; no CONTRIBUTING, PR template or CODEOWNERS | CI green on Python 3.11 and 3.14 (lint, types, coverage, secret scan, policy tests); PR template and CODEOWNERS; branch protection not enabled (GitHub reports it needs Pro for a private repository) | Partial | F-08, F-14, F-47 | evidence/15-modernization/EVD-R-02-ci-run-2-green.txt
Secrets | Password in source; credential-shaped values in .env.example | Removed from the tree; secret scan in CI; history kept; repository private; values treated as compromised (OQ-19) | Fixed in tree | F-09, F-10, F-11, F-12, F-13 | evidence/15-modernization/EVD-H-03-secret-scan-history.json
Infrastructure | Terraform with one local_file resource that emits a credential | Container recipe (Dockerfile, compose); Terraform provisions nothing; image never built; platform-neutral by decision (OQ-01) | Deferred | F-07, F-15, F-48 | docs/10-architecture/deployment-architecture.md
Resilience | No timeouts, retries or drills; incident runbook declares itself incomplete | Timeout, retry, circuit breaker; 5 failure drills pass; backup restore shown on the fixture | Fixed (repository level) | F-56 | evidence/28-resilience/EVD-M-03-drills/summary.json
Front end | Portal claimed in docs; scaffold with a no-op lint | Thin read-only operations view (OQ-06); browser test rewritten for it | Changed | F-05, F-06, F-52 | docs/20-application
Business value | No KPI data | Proxy KPIs frozen and re-measured; unchanged by design; no monetary benefit verified | Partial | F-57 | evidence/34-after-kpis/EVD-O-01-after-kpis.json
Encryption | No TLS, at-rest or key management statement | Unchanged; deferred until a platform exists | Deferred | F-16 | docs/42-executive/residual-risks.md

## File Inventory
Files and code lines per area: Repo 1.0 vs Repo 2.0
Tracked files under 07-logistics-shipment-fleet-routing-ops/. Code lines = .py .ts .rego .js .tf .sh. Counted with git at build time.
Area | Files 1.0 | Files 2.0 | Files change | Code lines 1.0 | Code lines 2.0 | Lines change
apps/api | 6 | 29 | 23 | 73 | 2118 | 2045
tests | 3 | 27 | 24 | 30 | 2198 | 2168
other (root files) | 10 | 24 | 14 | 0 | 6 | 6
scripts | 1 | 20 | 19 | 33 | 3541 | 3508
data | 11 | 14 | 3 | 0 | 0 | 0
evaluation | 0 | 11 | 11 | 0 | 624 | 624
docs | 9 | 9 | 0 | 0 | 0 | 0
apps/web | 3 | 8 | 5 | 10 | 100 | 90
observability | 1 | 5 | 4 | 0 | 0 | 0
.github | 1 | 3 | 2 | 0 | 0 | 0
etl | 2 | 3 | 1 | 20 | 337 | 317
policy | 1 | 2 | 1 | 12 | 323 | 311
legacy | 2 | 2 | 0 | 14 | 18 | 4
infra | 1 | 1 | 0 | 5 | 16 | 11
Total | 51 | 158 | 107 | 197 | 9281 | 9084

## Evidence Register
Evidence register: 146 hash-registered files
Source: evidence/EVIDENCE-INDEX.csv (derived from the per-folder MANIFEST.md files). Verified: every SHA-256 matches the file (EVD-R-03 verifier).
Evidence ID | Stage | Stage name | Phase | Folder | Type | Produced (UTC) | Findings addressed | Rubric criteria | Cited by | SHA-256 | Link
EVD-A-01-baseline-file-manifest | A | Engagement mobilisation and read-only orientation | 1 Understand | 00-preflight | sha256 | 2026-10-08T08:42:57Z | F-01 | R1 | docs/00-preflight/operating-contract/decision-log.md | 8eb89d1ff2dd835d78f823662e6dca0713b94034f71263504653d0cabba3fac2 | open
EVD-A-01-delivered-vs-committed | A | Engagement mobilisation and read-only orientation | 1 Understand | 00-preflight | csv | 2026-10-08T08:42:57Z | F-01 | R1 | docs/00-preflight/operating-contract/decision-log.md | dd2382a160a0c7586ca6ed393b90ec26b4113f6bb28e106fa2c1bcdeeb6ca30c | open
EVD-A-01-tag-verification | A | Engagement mobilisation and read-only orientation | 1 Understand | 00-preflight | txt | 2026-10-08T08:42:57Z | F-01 | R1 | docs/00-preflight/operating-contract/decision-log.md | a507d3d45cee3dd0598ca179c229ae213ef15c999ada6eb1353c4eea4be4b70b | open
EVD-A-02-spine-tree | A | Engagement mobilisation and read-only orientation | 1 Understand | 00-preflight | txt | 2026-10-08T08:42:57Z |  | R1 | docs/00-preflight/operating-contract/decision-log.md | 38db5b75d91b98521a40d52a5b623280bb9d038890ab23574a0ece327e2b0406 | open
EVD-A-03-toolchain-snapshot | A | Engagement mobilisation and read-only orientation | 1 Understand | 00-preflight | txt | 2026-10-08T09:00:00Z |  | R1 | docs/00-preflight/discovery/environment-snapshot.md | b9bc4bf6585621edcdd934895f923a0e2d4a643e0c5fed30c418715993b3231f | open
EVD-A-03c-runtime-upgrade-compat | A | Engagement mobilisation and read-only orientation | 1 Understand | 00-preflight | txt | 2026-10-08T09:10:00Z |  | R1 | docs/00-preflight/discovery/environment-snapshot.md | 4c48b3c48ba51da41bc0c7ef2a42b75002ab8738bffa9cedda85b2271aa6901a | open
EVD-A-03b-windows-host-snapshot | A | Engagement mobilisation and read-only orientation | 1 Understand | 00-preflight | txt | 2026-10-08T09:10:00Z |  | R1 | docs/00-preflight/discovery/environment-snapshot.md | 7e61ec7eb27d9126ac1ab9fa137a8eb0c009e5609ab3c56b8ab9d1340a82f345 | open
EVD-A-03d-windows-host-snapshot-2 | A | Engagement mobilisation and read-only orientation | 1 Understand | 00-preflight | txt | 2026-10-08T09:15:00Z |  | R1 | docs/00-preflight/discovery/environment-snapshot.md | 7569293ca130291d004dbb8cbfef68dd2dcb83cfcdad29c85b1197ad5ca135f6 | open
EVD-A-03e-operator-statement | A | Engagement mobilisation and read-only orientation | 1 Understand | 00-preflight | txt | 2026-10-08T09:20:00Z |  | R1 | docs/00-preflight/discovery/environment-snapshot.md | 328cdba5fb736a07f1af70c99fd01588b56e8b0ca4d5d8500c859f5c90ae0d18 | open
EVD-A-04-repo-tree-annotated | A | Engagement mobilisation and read-only orientation | 1 Understand | 00-preflight | txt | 2026-10-08T09:40:00Z |  | R1 | docs/00-preflight/discovery/ | 6dd1c997087a9a453650d2228a2a9a01aa075d9ba810905e3e0f83705c457347 | open
EVD-A-04b-data-profile | A | Engagement mobilisation and read-only orientation | 1 Understand | 00-preflight | txt | 2026-10-08T09:40:00Z |  | R1 | docs/00-preflight/discovery/ | b81c7055f0bad40deeb41ff0b76a0cb6b037420a5a4a575e5152d7c12e14d37e | open
EVD-A-05-confirmation-items | A | Engagement mobilisation and read-only orientation | 1 Understand | 00-preflight | txt | 2026-10-08T10:10:00Z |  | R1 | docs/00-preflight/operating-contract/operating-contract-readiness.md | 8c5b0b96519512cf2c80b94b9b92f167671669fcb6629cb32f8fe3ac6f6ec16c | open
EVD-A-06-ai-economics-profile | A | Engagement mobilisation and read-only orientation | 1 Understand | 00-preflight | json | 2026-10-08T10:30:00Z |  | R1 | docs/00-preflight/ai-economics/ | d38d6c61ea774cf11348a9a7c5a497c5eb77c04e78dfed773252fe9ca8d664d5 | open
EVD-A-07-stage-a-exit-checks | A | Engagement mobilisation and read-only orientation | 1 Understand | 00-preflight | txt | 2026-10-08T09:42:06Z |  | R1 | docs/00-preflight/stage-a-gate.md | f71de9f9325e9e14cd2def90df779de5e577db84683bf803e9720bf246fbf194 | open
EVD-A-04c-correlation-recount | A | Engagement mobilisation and read-only orientation | 1 Understand | 00-preflight | txt | 2026-10-08T10:18:49Z |  | R1 | decision-log D-012 | c2600111796cca839e726d805f30ac37f26904872fdff92ceaebd1663716707c | open
EVD-B-01-stage-b-checks | B | Qualification, stakeholders and problem framing | 1 Understand | 01-engagement | txt | 2026-10-08T09:43:22Z |  | R1 | docs/03-problem-value/stage-b-gate.md | 05f19134a27092776e4755f4e359dcb27afa0c23ab67821f2c9cf5ab6a638ee3 | open
EVD-C-05-data-profile | C | Baseline: KPIs, current state, root cause, behaviour | 1 Understand | 04-baseline-kpis | json | 2026-10-08T09:45:53Z |  | R1 | docs/04-baseline-kpis/ | 6314f00faa1df6c781714c3be2e946cae1b323858f1b435868989a8f4dced202 | open
EVD-C-05-profile | C | Baseline: KPIs, current state, root cause, behaviour | 1 Understand | 04-baseline-kpis | py | 2026-10-08T09:45:54Z |  | R1 | docs/04-baseline-kpis/ | 7c6f7f2b4fd3b69f6dc6b980a65d2f530219d69e9e53a2657e9d70ff34f0247a | open
EVD-C-04-flow-to-code-trace | C | Baseline: KPIs, current state, root cause, behaviour | 1 Understand | 05-current-state | md | 2026-10-08T09:47:28Z |  | R1 | docs/05-current-state/business-workflow-map.md | 4ddd2316209f21774efc175f323585b52c0363bda79b040be3515c3fbd7559f1 | open
EVD-C-02-quickstart-transcript | C | Baseline: KPIs, current state, root cause, behaviour | 1 Understand | 07-repo-assessment | txt | 2026-10-08T09:45:54Z | F-02 | R1 | docs/07-repo-assessment/baseline-behaviour.md | 74e85bd8cec2ade87fc4ccf8a95b40552928010bfd689e761b21868fdf541581 | open
EVD-C-03-transcript | C | Baseline: KPIs, current state, root cause, behaviour | 1 Understand | 07-repo-assessment | txt | 2026-10-08T09:45:54Z |  | R1 | docs/07-repo-assessment/baseline-behaviour.md | e00e2c43b291f1a06e7144f029873e2b4422672353800328fc2534d30060b743 | open
EVD-C-03-junit | C | Baseline: KPIs, current state, root cause, behaviour | 1 Understand | 07-repo-assessment | xml | 2026-10-08T09:45:54Z |  | R1 | docs/07-repo-assessment/baseline-behaviour.md | 1d96dc44eb81588a1155ba4566d8d87ab7ef22d62ba21b803f7835d3926ca8da | open
EVD-C-03-coverage | C | Baseline: KPIs, current state, root cause, behaviour | 1 Understand | 07-repo-assessment | xml | 2026-10-08T09:45:54Z |  | R1 | docs/07-repo-assessment/baseline-behaviour.md | 85210479df1b835c07459cca3a26494695ede817d7399bc85133811e92b607e8 | open
EVD-C-07-findings-index | C | Baseline: KPIs, current state, root cause, behaviour | 1 Understand | 07-repo-assessment | json | 2026-10-08T09:47:28Z |  | R1 | docs/07-repo-assessment/technical-debt-register.md | 6c387bfd6ea34ba4aca6464d7bcea97e164f439d89acc063516ecec85e016a98 | open
EVD-C-08-characterization-junit | C | Baseline: KPIs, current state, root cause, behaviour | 1 Understand | 07-repo-assessment | xml | 2026-10-08T09:48:24Z | F-19;F-20;F-24;F-32;F-51 | R1 | docs/07-repo-assessment/stage-c-gate.md | b35040581e79ee0e1b912f8399b855e60ef591ad76c24faa27eb7c0169ffd90e | open
EVD-C-09-stage-c-exit-checks | C | Baseline: KPIs, current state, root cause, behaviour | 1 Understand | 07-repo-assessment | txt | 2026-10-08T09:48:24Z |  | R1 | docs/07-repo-assessment/stage-c-gate.md | 61b3292ae9002e9da7fbdc5d30c3074b8c983a2ac01c20c0fd1fdfadd44b9828 | open
EVD-E-04-stage-e-checks | E | Intervention qualification and initial PRD | 2 Define | 08-ai-qualification | txt | 2026-10-08T09:55:03Z |  | R4 | docs/09-initial-prd/stage-e-gate.md | 56b7058b10ff961bc3091af9007b241a45b7f3ccc649790a6345f1f640e069c6 | open
EVD-E-03-requirement-trace | E | Intervention qualification and initial PRD | 2 Define | 09-initial-prd | csv | 2026-10-08T09:55:03Z |  | R4 | docs/09-initial-prd/initial-prd-traceability.md | 079f95fb2f36f6dc60697bafebf6720ebb4696699722d19f7335786cb4a00453 | open
EVD-F-01-adr-index | F | Target architecture, data and context, specs, traceability | 2 Define | 10-architecture | txt | 2026-10-08T10:03:32Z | F-53 | R4 | stage-f-gate.md (F-X1) | 4cae717c359d65180ef203aeda719971c6f37e405a160e033495cc8bcf5d450d | open
EVD-D-01-field-coverage | D | Semantic layer extraction | 2 Define | 11-data-context | csv | 2026-10-08T09:53:26Z | F-37 | R2 | docs/11-data-context/stage-d-gate.md | 298054a6d5c07cc41202e4816df2e3f90438d03b9e8044747e3c06828fce293c | open
EVD-D-02-enum-violations | D | Semantic layer extraction | 2 Define | 11-data-context | csv | 2026-10-08T09:53:26Z |  | R2 | docs/11-data-context/stage-d-gate.md | 358e7392b8fad0b672ac5a4ee4b0e352b863e544f23a1ba9a637aac1c51f2ea7 | open
EVD-D-03-rule-to-gap-trace | D | Semantic layer extraction | 2 Define | 11-data-context | csv | 2026-10-08T09:53:26Z |  | R2 | docs/11-data-context/stage-d-gate.md | 5388fb6ad5f0454598a0488454a4012d3de54936d2defb84bbce6134f3c5a582 | open
EVD-D-04-access-semantics-matrix | D | Semantic layer extraction | 2 Define | 11-data-context | csv | 2026-10-08T09:53:26Z |  | R2 | docs/11-data-context/stage-d-gate.md | f95609856b8284299d323c48befa7e688f60c55d31c5ef508581d05121b005c8 | open
EVD-D-05-rule-baseline | D | Semantic layer extraction | 2 Define | 11-data-context | json | 2026-10-08T09:53:26Z |  | R2 | docs/11-data-context/stage-d-gate.md | d44af9df668fa79e00af0ee2da9c0cdad84ff6e6bf9ac1c8b225d9d085132d55 | open
EVD-D-05-semantic-layer-junit | D | Semantic layer extraction | 2 Define | 11-data-context | xml | 2026-10-08T09:53:26Z |  | R2 | docs/11-data-context/stage-d-gate.md | cb1fc7cbbef53af7b1e21ab6a657e65dcc0b84dcfe178ca91dad5ebb127dae45 | open
EVD-D-05-generated-semantic-layer | D | Semantic layer extraction | 2 Define | 11-data-context | json | 2026-10-08T09:53:26Z |  | R2 | docs/11-data-context/stage-d-gate.md | edf62772dc55687db93dd20f3e520331db0e5f247d936c0ced401cee79083bf2 | open
EVD-D-06-semantic-v2-junit | D | Semantic layer extraction | 2 Define | 11-data-context | xml | 2026-10-08T16:53:46Z |  | R2 | docs/11-data-context/semantic-layer-v2-alignment.md | fc7501deca0483cf68eb7977ae3c6595f49e187be7338b691fcd27e051c55fd7 | open
EVD-D-06-semantic-layer-v2-hashes | D | Semantic layer extraction | 2 Define | 11-data-context | json | 2026-10-08T16:53:46Z |  | R2 | docs/11-data-context/semantic-layer-v2-alignment.md | cffd158ffa517b9874ceb7b1e4ee15fc535273b9d437ad04a95bede40eb19fdf | open
EVD-F-03-openapi | F | Target architecture, data and context, specs, traceability | 2 Define | 12-specs | yaml | 2026-10-08T10:02:44Z | F-25;F-43;F-50 | R4 | docs/12-specs/spec-readiness.md; stage-f-gate.md | 6016a47d34dccadb44c6f7237cd3077f44edce88f5029801d5d1249272215c87 | open
EVD-F-03-openapi-validation | F | Target architecture, data and context, specs, traceability | 2 Define | 12-specs | txt | 2026-10-08T10:02:44Z | F-25;F-43;F-50 | R4 | docs/12-specs/spec-readiness.md; stage-f-gate.md | 0633960f82600f6fbf80d68cd7b6e60e9f2d87242ec53df855af06b55a35cd1a | open
EVD-F-03-schema-checks | F | Target architecture, data and context, specs, traceability | 2 Define | 12-specs | txt | 2026-10-08T10:02:44Z | F-25;F-43;F-50 | R4 | docs/12-specs/spec-readiness.md; stage-f-gate.md | 8690d9106e92bc96d0d4c207a2bc2f377185076fab46e868a6e37d0ad708b26d | open
EVD-F-03-route-coverage-diff | F | Target architecture, data and context, specs, traceability | 2 Define | 12-specs | txt | 2026-10-08T10:02:44Z | F-25;F-43;F-50 | R4 | docs/12-specs/spec-readiness.md; stage-f-gate.md | 9dbd1b3c0b3b193b3bb934a5ed36415c2b524817950f82f7f385bb18822a41f3 | open
EVD-F-04-finding-coverage-matrix | F | Target architecture, data and context, specs, traceability | 2 Define | 13-traceability | csv | 2026-10-08T10:03:32Z |  | R4;R5 | stage-f-gate.md (F-X8) | 055a52f15d9daafa8d76bc642da760ea3a404790ac7d0fcefbb9f76ba1016821 | open
EVD-F-05-stage-f-exit-checks | F | Target architecture, data and context, specs, traceability | 2 Define | 13-traceability | txt | 2026-10-08T10:03:33Z |  | R4 | stage-f-gate.md | 1df22f4e7472cff0bdb6e7bf8948a79ac0ffb468ca210b1d70278c32fa003f4e | open
EVD-F-04b-finding-disposition-final | F | Target architecture, data and context, specs, traceability | 2 Define | 13-traceability | csv | 2026-10-08T12:27:21Z |  | R5 | final-gate.md; requirement-disposition-matrix.md | 24dc4df12754670d842a7f1d8fb2d8dfa03eb8214dd35758a7e26577a6e774d1 | open
EVD-G-01-backlog-finding-coverage | G | Transformation and migration planning | 2 Define | 14-transformation | txt | 2026-10-08T10:04:56Z |  | R3 | stage-g-gate.md | f64b2b4c088a555f2f8092bff98371c1073f4215504b19a776bae50aeadcbc95 | open
EVD-G-04-authorisation-record | G | Transformation and migration planning | 2 Define | 14-transformation | txt | 2026-10-08T10:04:56Z | F-08 | R3 | stage-g-gate.md | 88f1b4321b2f75114ce9c1a23866a289757ac3f81358180c55b323d15d2e4679 | open
EVD-G-05-stage-g-exit-checks | G | Transformation and migration planning | 2 Define | 14-transformation | txt | 2026-10-08T10:05:18Z |  | R3 | stage-g-gate.md | 2821273226c7a28d49e897479703bdf974cf8c160f04beb8dc6055d8c55397ad | open
EVD-H-01-pipeline-run | H | Repo 2.0 modernisation and validation | 3 Build | 15-modernization | txt | 2026-10-08T12:12:48Z |  | R2 | docs of step H1 | 943f500b2da991e6bfcf1bba9740cfe8839bde806197ba9ac03d98cad007bd2b | open
EVD-H-02-quickstart-after | H | Repo 2.0 modernisation and validation | 3 Build | 15-modernization | txt | 2026-10-08T12:12:48Z | F-02;F-03;F-04 | R2 | docs of step H2 | 253337ce0f1b3e20361e42b612628b9447c629ce33633ea48bd88696d8310c70 | open
EVD-H-03-secret-scan-history | H | Repo 2.0 modernisation and validation | 3 Build | 15-modernization | json | 2026-10-08T12:12:48Z | F-09;F-10;F-11;F-12;F-14 | R2 | docs of step H3 | 473b47bb982b7ab65985c869a7f35068253b7c3719d610e9ad90ed8f85849a4c | open
EVD-H-03-secret-scan | H | Repo 2.0 modernisation and validation | 3 Build | 15-modernization | json | 2026-10-08T12:12:48Z | F-09;F-10;F-11;F-12;F-14;F-15 | R2 | docs of step H3 | 9be399823ccf9be244917852a3f19b4ee67b5e5d2c813fae5b7f4c4fd20c4dab | open
EVD-H-04-negative-access-tests | H | Repo 2.0 modernisation and validation | 3 Build | 15-modernization | txt | 2026-10-08T12:12:48Z | F-17;F-18 | R2 | docs of step H4 | c724516d79f2e15cce8017516c2a82a30c2eb663c4fe08b5cc83b181213eb2eb | open
EVD-H-04-policy-allow-deny-matrix | H | Repo 2.0 modernisation and validation | 3 Build | 15-modernization | csv | 2026-10-08T12:12:48Z | F-17;F-18;F-21 | R2 | docs of step H4 | f838baffa93da9043a972b23f70f36a84f9442848d2805d4a2d029f4a96ad25a | open
EVD-H-05-behaviour-change | H | Repo 2.0 modernisation and validation | 3 Build | 15-modernization | md | 2026-10-08T12:12:48Z |  | R2 | docs of step H5 | cd41c7f450672e8dcb52cf26938be81a1df6c6df40a6527761e07202370b2f23 | open
EVD-H-06-etl-dq-report | H | Repo 2.0 modernisation and validation | 3 Build | 15-modernization | json | 2026-10-08T12:12:48Z | F-33;F-34;F-35;F-36;F-38;F-40;F-41;F-54;F-58;F-59;F-61;F-62 | R2 | docs of step H6 | 1f091a63cc2100d80f936f5d6649fd30561f2f009820ef1e63c79f81f9520ed7 | open
EVD-H-07-ai-gateway-results | H | Repo 2.0 modernisation and validation | 3 Build | 15-modernization | json | 2026-10-08T12:12:48Z | F-22;F-23;F-25;F-27;F-28;F-29 | R2 | docs of step H7 | 38fe45eb845bc0d5c3aebbc45d155f9d0a2997ee758cf39c497312d245b1aec6 | open
EVD-H-08-trace-sample | H | Repo 2.0 modernisation and validation | 3 Build | 15-modernization | json | 2026-10-08T12:12:48Z | F-42;F-44;F-45 | R3 | docs of step H8 | 5b79ef4cf9cc76f6b5d6e39dd9300d709b0e7633f933e1c21029adc4b07a1e88 | open
EVD-R-02-ci-run-1-failed | R | Executive defence, as-built PRD, production evidence pack | 5 Defend | 15-modernization | txt | 2026-10-08T12:20:58Z | F-47 | R5 | residual-risks.md; lessons-learned.md | 23711892040269c52df2765ce8ae5dfa695369196cf274543ce27f000826a70c | open
EVD-R-01-final-verification | R | Executive defence, as-built PRD, production evidence pack | 5 Defend | 15-modernization | txt | 2026-10-08T12:20:58Z | F-13;F-15;F-23;F-27;F-30;F-31;F-45 | R5 | production-readiness-decision.md | 510e7971405b8f1f097dc385fcbe5cb700a6ed54d5011e7108a64bc83b7db92f | open
EVD-R-02-ci-run-2-green | R | Executive defence, as-built PRD, production evidence pack | 5 Defend | 15-modernization | txt | 2026-10-08T12:23:28Z | F-04;F-06;F-08;F-21;F-47 | R5 | production-readiness-decision.md | ecc80c2198e52f243b4fad863caae96b5c55ec8c2d8c9f451f5306e8222a6b28 | open
EVD-H-09-smoke | H | Repo 2.0 modernisation and validation | 3 Build | 16-repo-validation | txt | 2026-10-08T12:12:48Z | F-54;F-55 | R2 | docs of step H9 | e3d44aec2bed164620555f0b9ae4deafa1d4a35c62eecdf6e14cb4417681b80f | open
EVD-H-10-behaviour-diff | H | Repo 2.0 modernisation and validation | 3 Build | 16-repo-validation | csv | 2026-10-08T12:12:48Z |  | R1 | docs of step H10 | c78a8433c06d9266db854f14d8ee3393ff348a4dd42dc5cdd032114fc0c92b58 | open
EVD-H-11-architecture-imports | H | Repo 2.0 modernisation and validation | 3 Build | 16-repo-validation | txt | 2026-10-08T12:12:48Z |  | R2 | docs of step H11 | cf22df29cba03e3f711d476afbc4a1e74862bdb09cdfb53982ac28f9dcc7634e | open
EVD-H-11-dependency-audit | H | Repo 2.0 modernisation and validation | 3 Build | 16-repo-validation | json | 2026-10-08T12:12:48Z |  | R2 | docs of step H11 | 97b9424c9b9bdb1905993a93f0557a2705afc63f2c4421c46d1079d3e24d756d | open
EVD-H-11-pytest-coverage | H | Repo 2.0 modernisation and validation | 3 Build | 16-repo-validation | txt | 2026-10-08T12:12:48Z |  | R2 | docs of step H11 | 4c4904decbe976b76f17e0b2520d1911bee730985864868e999a12a875dafc46 | open
EVD-H-11-static-analysis | H | Repo 2.0 modernisation and validation | 3 Build | 16-repo-validation | txt | 2026-10-08T12:12:48Z |  | R2 | docs of step H11 | a133801206f5d18f1b8a2a73b357919ecee21be91088555fcfe65cc6f14ee960 | open
EVD-H-11-tg5-tg6 | H | Repo 2.0 modernisation and validation | 3 Build | 16-repo-validation | txt | 2026-10-08T12:12:48Z |  | R2 | docs of step H11 | 9d4ebee480f60ba0c0a21d28ec290582e585d54b6b7b71e630d88151374fa030 | open
EVD-J-02-dataset-manifest | J | Intelligence core, application, integration and agents | 3 Build | 19-intelligence | json | 2026-10-08T12:12:48Z |  | R2;R4 | docs of step J2 | 12f6d1e61249453395f330787076dddd9376797833fe8a27632fd34e3c444479 | open
EVD-J-03-eval-run1 | J | Intelligence core, application, integration and agents | 3 Build | 19-intelligence | json | 2026-10-08T12:12:48Z |  | R2;R4 | docs of step J3 | 831889be4bda61a9bdd8ed338a22318145df97be03376e7d7587985c4126e937 | open
EVD-J-03-eval-run2-after-remediation | J | Intelligence core, application, integration and agents | 3 Build | 19-intelligence | json | 2026-10-08T12:12:48Z |  | R2;R4 | docs of step J3 | 3f729728c7e621fc037ceb2cbe9c829882f019fa74ba8119302bc8bc46bd5f3d | open
EVD-J-04-browser-e2e-script.py | J | Intelligence core, application, integration and agents | 3 Build | 20-application | txt | 2026-10-08T12:12:48Z | F-05;F-52 | R2;R4 | docs of step J4 | 532ea7c45747e07453e50bb5fe116d96c223507d924c4444fa0656e51854f8f3 | open
EVD-J-04-browser-e2e | J | Intelligence core, application, integration and agents | 3 Build | 20-application | json | 2026-10-08T12:12:48Z | F-05;F-52 | R2;R4 | docs of step J4 | 79064bd7b6b0df59ac517e1d2bed3e32087836a44e8bdecb781b8b2fbb3c49bd | open
EVD-J-04-screenshot-decision | J | Intelligence core, application, integration and agents | 3 Build | 20-application | png | 2026-10-08T12:12:48Z | F-05;F-52 | R2;R4 | docs of step J4 | e8176a1a476d499d1c1f6bba62a09d0ad0d468db368e65aef74a6fb8eee19cbb | open
EVD-J-04-screenshot-suggestion | J | Intelligence core, application, integration and agents | 3 Build | 20-application | png | 2026-10-08T12:12:48Z | F-05;F-52 | R2;R4 | docs of step J4 | 4b8ef6b6919d7688e98f0104a1f978a3e86c503fdacad4f5c2d41e227c3956b2 | open
EVD-J-05-saga-simulation | J | Intelligence core, application, integration and agents | 3 Build | 21-integration | json | 2026-10-08T12:12:48Z | F-39 | R2;R4 | docs of step J5 | 66c0a6ef457835fb26ed61804acde5eff5cc78e3e9272c0beeb9e183ef863fe7 | open
EVD-J-05-saga-tests | J | Intelligence core, application, integration and agents | 3 Build | 21-integration | txt | 2026-10-08T12:12:48Z | F-39 | R2;R4 | docs of step J5 | cd8eadbda2dd4ee54ccf1325e3fdd59fc09ec71d6c1b15a27534027975beab06 | open
EVD-K-01-human-control-tests | K | Human control, security, privacy, responsible AI, governance | 4 Prove | 23-human-control | txt | 2026-10-08T12:12:48Z | F-26 | R3 | docs of step K1 | ebd91a777fa2223e03d14f0f9a949ecafa3b80e17a0da4cf179519ccde821828 | open
EVD-K-02-security-suite | K | Human control, security, privacy, responsible AI, governance | 4 Prove | 24-security-privacy | txt | 2026-10-08T12:12:48Z |  | R3 | docs of step K2 | 9e84ddad8bd61c9cdf38f4948b387358b44c5f5e0ff8ee88b85f23c6aa1fd537 | open
EVD-K-02b-security-suite-after-m1 | K | Human control, security, privacy, responsible AI, governance | 4 Prove | 24-security-privacy | txt | 2026-10-08T12:12:48Z |  | R3 | docs of step K2 | deebe2780f9a2931192922f3af183473ca9c1b1a2da63e1869a64b6ae1f43859 | open
EVD-L-02-final-eval-run | L | TEVV and AI red teaming | 4 Prove | 26-tevv | json | 2026-10-08T12:12:48Z | F-29 | R3;R4 | docs of step L2 | dfdf29d208c4cdc05911c3fe8c76ba6ccfe66ccbd6d9a0677aee10d40c8ee54e | open
EVD-L-03-redteam-baseline | L | TEVV and AI red teaming | 4 Prove | 26-tevv | json | 2026-10-08T12:12:48Z | F-17;F-19;F-20;F-22;F-24;F-26;F-30;F-31;F-32 | R3 | docs of step L3 | 690911c90695c307f620ac56aec88e8d0da9732b4f6405dbf9c381e38df9213f | open
EVD-L-03-redteam-v2 | L | TEVV and AI red teaming | 4 Prove | 26-tevv | json | 2026-10-08T12:12:48Z | F-17;F-19;F-20;F-22;F-24;F-26;F-30;F-31;F-32;F-60 | R3 | docs of step L3 | b6f65533d6d71145d1d98da52ee5886590871091c704bc514e07984327d03356 | open
EVD-M-01-bandit | M | Hardening, resilience, incident response, BC/DR | 4 Prove | 27-hardening | json | 2026-10-08T12:12:48Z | F-49 | R2 | docs of step M1 | 8a6e8b7670108e14cfedbe5432c7dc3a7b9b94fa189a5ede434b50772e32baa6 | open
EVD-M-01-pip-audit-dev | M | Hardening, resilience, incident response, BC/DR | 4 Prove | 27-hardening | json | 2026-10-08T12:12:48Z | F-49 | R2 | docs of step M1 | 70ef1b6fa497f5d480a0f3ea6e5841f0434f7d16c4d23be138e086f178b54abf | open
EVD-M-01-pip-audit-runtime | M | Hardening, resilience, incident response, BC/DR | 4 Prove | 27-hardening | json | 2026-10-08T12:12:48Z | F-49 | R2 | docs of step M1 | 97b9424c9b9bdb1905993a93f0557a2705afc63f2c4421c46d1079d3e24d756d | open
EVD-M-01-sbom-dev.cdx | M | Hardening, resilience, incident response, BC/DR | 4 Prove | 27-hardening | json | 2026-10-08T12:12:48Z | F-49 | R2 | docs of step M1 | 34d4a0df90df63d0c2ae3cd90a86f0db75f78f3b8ec90b219cdf11a35316cf1d | open
EVD-M-01-sbom-runtime.cdx | M | Hardening, resilience, incident response, BC/DR | 4 Prove | 27-hardening | json | 2026-10-08T12:12:48Z | F-49 | R2 | docs of step M1 | 7b6b270a171dbb86fec07b9dd599d04792188e95a3b08805269d0f15e4c34395 | open
EVD-M-02-load-probe | M | Hardening, resilience, incident response, BC/DR | 4 Prove | 28-resilience | json | 2026-10-08T12:12:48Z |  | R2 | docs of step M2 | fe069284369b402e6ad264b65bcec643eafb054804d6877036f375ae34d212af | open
EVD-M-02-resilience-tests | M | Hardening, resilience, incident response, BC/DR | 4 Prove | 28-resilience | txt | 2026-10-08T12:12:48Z |  | R2 | docs of step M2 | c6191583172113272d2031f3ed399ca7461a0dfc6ed23de62e9c8d1e17ce2c3e | open
EVD-M-03-drills/drill-1-correlation-ids | M | Hardening, resilience, incident response, BC/DR | 4 Prove | 28-resilience | json | 2026-10-08T12:12:48Z |  | R2 | docs of step ? | 2678bb9b1575124a32cc31db1c307f5b7be08ff6036af728a55099bcd06c7bc2 | open
EVD-M-03-drills/drill-2-ai-gateway-timeout | M | Hardening, resilience, incident response, BC/DR | 4 Prove | 28-resilience | json | 2026-10-08T12:12:48Z |  | R2 | docs of step ? | 50001fe1c3022b876dcd94b1e7c511b7d99c7297dfb1378ccb1017df3a331def | open
EVD-M-03-drills/drill-3-duplicate-replay | M | Hardening, resilience, incident response, BC/DR | 4 Prove | 28-resilience | json | 2026-10-08T12:12:48Z |  | R2 | docs of step ? | 2e780ff9b4b749a1918f0754dd988271dd3de16de8a3a765f9f03513f388ba6b | open
EVD-M-03-drills/drill-4-stale-master-data | M | Hardening, resilience, incident response, BC/DR | 4 Prove | 28-resilience | json | 2026-10-08T12:12:48Z |  | R2 | docs of step ? | 8f8f3e35a1bc319fd0c88b56313934cb59126d16f944f3a0899c884bc09bf9be | open
EVD-M-03-drills/drill-5-legacy-partial-failure | M | Hardening, resilience, incident response, BC/DR | 4 Prove | 28-resilience | json | 2026-10-08T12:12:48Z |  | R2 | docs of step ? | 9d7180652d755931ed94dfd855a33587ac1d8d1dc5012715d3769f0de39c0355 | open
EVD-M-03-drills/summary | M | Hardening, resilience, incident response, BC/DR | 4 Prove | 28-resilience | json | 2026-10-08T12:12:48Z |  | R2 | docs of step ? | eec9e4e654674cf439c8ed4a888514c0e2485679fdd7f61bc513294b343f00ac | open
EVD-M-03-resilience-tests-after-drills | M | Hardening, resilience, incident response, BC/DR | 4 Prove | 28-resilience | txt | 2026-10-08T12:12:48Z |  | R2 | docs of step M3 | 9c509bda36ef6a69faa52ede33666646c59e27907c5e1c8e1027767115c4b8a8 | open
EVD-M-04-tabletop-simulation | M | Hardening, resilience, incident response, BC/DR | 4 Prove | 29-incident-bcdr | json | 2026-10-08T12:12:48Z | F-56 | R2 | docs of step M4 | 4b0a559a37a34090a95c38774c364d70c4b012dc734a41a55a2171aaaba8cb10 | open
EVD-N-03-backup-restore | N | Release, observability, FinOps, vendor risk | 4 Prove | 30-release | json | 2026-10-08T12:12:48Z |  | R3 | docs of step N3 | a2bf3c55a72cf2c96b00ad4b938ef0f78edeee97df911f918e8e95a2b6a4268e | open
EVD-N-01-full-suite | N | Release, observability, FinOps, vendor risk | 4 Prove | 31-observability | txt | 2026-10-08T12:12:48Z | F-46 | R3 | docs of step N1 | dcd4e5b0fa68b3dfb016e6b78802228458437b48d4f3d1de44da866debd0c916 | open
EVD-N-01-observability-validation | N | Release, observability, FinOps, vendor risk | 4 Prove | 31-observability | json | 2026-10-08T12:12:48Z | F-46 | R3 | docs of step N1 | b18c9aebb64f1dabeec34b6564f2d4e941468881eca1aa93229300a88af90485 | open
EVD-N-01b-full-suite-after-p | N | Release, observability, FinOps, vendor risk | 4 Prove | 31-observability | txt | 2026-10-08T12:12:48Z |  | R3 | docs of step N1 | d05daff4a35eb0de4423bbce4f3887cd4c58c2116bfb10cfc36c642e4d19d842 | open
EVD-N-02-reconstruction | N | Release, observability, FinOps, vendor risk | 4 Prove | 31-observability | json | 2026-10-08T12:12:48Z | F-42;F-43;F-44;F-45 | R1;R3;R4 | docs of step N2 | 1eed65aa84641d9e7d564b91a99baa04006f1ba05ca26590cdae5a8181e6c241 | open
EVD-N-04-finops-model | N | Release, observability, FinOps, vendor risk | 4 Prove | 32-finops | json | 2026-10-08T12:12:48Z |  | R3 | docs of step N4 | 207c99d898ebf3cee5d81c1a7990823b06c41fd606117872a91936195f437bac | open
EVD-O-01-after-kpis | O | Outcome measurement, value leakage, benefits | 5 Defend | 34-after-kpis | json | 2026-10-08T12:12:48Z | F-57 | R1 | docs of step O1 | 3708e637ef8963bda70458efcea4a75f6521f9972ce5610e4ffc73a7b2dea717 | open
EVD-O-03-benefit-model | O | Outcome measurement, value leakage, benefits | 5 Defend | 36-benefits | json | 2026-10-08T12:12:48Z |  | R1 | docs of step O3 | 2afe6092b217cb967a19100ba71c32fb09eadc66e7fdd0bfe0112e7cbffc7e52 | open
EVD-P-02-operator-exercises | P | Operating model, handover, drift, scale, retirement | 5 Defend | 38-handover | json | 2026-10-08T12:12:48Z | F-07 | R3 | docs of step P2 | 0482bd0cf4b1edf59e04ea08f2b7ab4a6ba2d2d45fc2e423b430b1e3be6780ab | open
EVD-P-03-drift-check-clean | P | Operating model, handover, drift, scale, retirement | 5 Defend | 39-continuous-improvement | json | 2026-10-08T12:12:48Z |  | R3 | docs of step P3 | 68b946cf2f1147b84059905b7a80e23bdaeea3e6bc06eca8a3492b7a59d8258f | open
EVD-P-03-drift-check-drifted | P | Operating model, handover, drift, scale, retirement | 5 Defend | 39-continuous-improvement | json | 2026-10-08T12:12:48Z |  | R3 | docs of step P3 | 702f90ca3f04232249f31c3dc207c67aee97f3e3afa0b9914b9f6df54adc29a4 | open
EVD-Q-01-preregistration | Q | Model portability validation and demonstration | 5 Defend | 40-scale | json | 2026-10-08T12:12:28Z |  | R2 | semantic-layer-portability-test.md | d050b98fe3a419f360f48be9edb646e952ccd3d08488cd5639d41556da875014 | open
EVD-Q-02-comparison | Q | Model portability validation and demonstration | 5 Defend | 40-scale | csv | 2026-10-08T12:12:28Z |  | R2 | model-comparison.md | 25b4aaddc9c676a3d13545292d79e791d6b3296d750047d7eae28ed004b32656 | open
EVD-Q-04-harness-accept | Q | Model portability validation and demonstration | 5 Defend | 40-scale | py | 2026-10-08T13:09:26Z |  | R2;R5 | semantic-layer-portability-test.md | 65f2ebc3273aeb575ca6b1d1551fcf12293d567872c79d48e6e4d5347341c433 | open
EVD-Q-04-adapter-a | Q | Model portability validation and demonstration | 5 Defend | 40-scale | py | 2026-10-08T13:09:26Z |  | R2;R5 | semantic-layer-portability-test.md | ec136b28fef0c35ad0f1279b7fba6db491ecfa33d27e0a7770fab7af8d7098da | open
EVD-Q-04-build-brief | Q | Model portability validation and demonstration | 5 Defend | 40-scale | md | 2026-10-08T13:09:26Z |  | R2;R5 | semantic-layer-portability-test.md | 9756dedad564cf4092e4f784cd961cfcb610f4f1c61f73c37f0b0393dd3afb6c | open
EVD-Q-04-bundle-sha256 | Q | Model portability validation and demonstration | 5 Defend | 40-scale | txt | 2026-10-08T13:09:26Z |  | R2;R5 | semantic-layer-portability-test.md | 57868ce78c130e64db6e1cca9dc0e1d425a51c060df3eca101991ddaca1b9cc2 | open
EVD-Q-04-control-A-eval | Q | Model portability validation and demonstration | 5 Defend | 40-scale | json | 2026-10-08T13:09:26Z |  | R2;R5 | semantic-layer-portability-test.md | ca535583e1339ad66c87fc97de620f2616eb82276dea42417d98b9925e98fb79 | open
EVD-Q-04-control-A-http | Q | Model portability validation and demonstration | 5 Defend | 40-scale | json | 2026-10-08T13:09:26Z |  | R2;R5 | semantic-layer-portability-test.md | 82350bea067346789f169cb4e3669209320f17a6ac8f12fa062c8901e058217b | open
EVD-Q-04-harness-preregistration | Q | Model portability validation and demonstration | 5 Defend | 40-scale | json | 2026-10-08T13:09:26Z |  | R2;R5 | semantic-layer-portability-test.md | 8b622a5c88105d75963a352b0007f06a023a32970947beb42d32f395047c2e9b | open
EVD-Q-05-model-b-transcript | Q | Model portability validation and demonstration | 5 Defend | 40-scale | jsonl | 2026-10-08T13:51:27Z |  | R2;R5 | semantic-layer-portability-test.md; model-comparison.md | 7fb1472046dfee8e3edb03cd87e5574d592b085a9ef7e65c69d4885f2c17412d | open
EVD-Q-05-model-b-meta | Q | Model portability validation and demonstration | 5 Defend | 40-scale | json | 2026-10-08T13:51:27Z |  | R2;R5 | semantic-layer-portability-test.md; model-comparison.md | a3f23119b8f49abb20c467029423b67a2b0d071f82b935a351304e2986295afa | open
EVD-Q-05-model-b-build.tar | Q | Model portability validation and demonstration | 5 Defend | 40-scale | gz | 2026-10-08T13:51:27Z |  | R2;R5 | semantic-layer-portability-test.md; model-comparison.md | 14d503b12422353fb7c1a0f1bff5166c02c6cfca3570023e89bf3e9bd61f2801 | open
EVD-Q-05-model-b-notes | Q | Model portability validation and demonstration | 5 Defend | 40-scale | md | 2026-10-08T13:51:27Z |  | R2;R5 | semantic-layer-portability-test.md; model-comparison.md | 86af3789f56bc6fe86c83e69501187c89fe7bf97fcd2040004e247f251939e7f | open
EVD-Q-05-model-b-eval | Q | Model portability validation and demonstration | 5 Defend | 40-scale | json | 2026-10-08T13:51:27Z |  | R2;R5 | semantic-layer-portability-test.md; model-comparison.md | d1c521804b2171cc9f7c091da0e71a90fa93c7c02fa9ea3aa1afbb92de46984e | open
EVD-Q-05-model-b-http | Q | Model portability validation and demonstration | 5 Defend | 40-scale | json | 2026-10-08T13:51:27Z |  | R2;R5 | semantic-layer-portability-test.md; model-comparison.md | 8d57a3f6a79ebed41c9ffa07a01882326f4a4dbe1973440463f7c971900eb6d3 | open
EVD-Q-05-model-b-http-supp-ai_agent | Q | Model portability validation and demonstration | 5 Defend | 40-scale | json | 2026-10-08T13:51:27Z |  | R2;R5 | semantic-layer-portability-test.md; model-comparison.md | 89b7630c1722771b4621d39212412b42718c3d5e4226b98207378a21216eb93f | open
EVD-Q-05-harness-accept-supp | Q | Model portability validation and demonstration | 5 Defend | 40-scale | py | 2026-10-08T13:51:27Z |  | R2;R5 | semantic-layer-portability-test.md; model-comparison.md | e6344f3f760bb854600cd8d53a8f996ab7f4541dd45bd349938c8dc8890ff0a2 | open
EVD-Q-05-posthoc-recommendation-class | Q | Model portability validation and demonstration | 5 Defend | 40-scale | txt | 2026-10-08T13:51:27Z |  | R2;R5 | semantic-layer-portability-test.md; model-comparison.md | f23bff6e2a539d6609202c0b259581e08a3c5fbc82503554e3b75ffe9804faa3 | open
EVD-Q-05-posthoc-recommendation-class | Q | Model portability validation and demonstration | 5 Defend | 40-scale | py | 2026-10-08T13:51:27Z |  | R2;R5 | semantic-layer-portability-test.md; model-comparison.md | 5c7b388638b6d8216d983ef0de2f87ad8e6d674513b224de70f661e4e76f449b | open
EVD-Q-05-model-b-prompt | Q | Model portability validation and demonstration | 5 Defend | 40-scale | md | 2026-10-08T13:51:27Z |  | R2;R5 | semantic-layer-portability-test.md; model-comparison.md | 7fa9ab4ea1864e497629ab86ceb56d18a5125b245d5b71ef3b0fcd6fe98c3f6b | open
EVD-Q-05-blindness-check | Q | Model portability validation and demonstration | 5 Defend | 40-scale | txt | 2026-10-08T13:51:27Z |  | R2;R5 | semantic-layer-portability-test.md; model-comparison.md | d46562a75311829ba853d7d34130692d7684676fc33613179fb7c47465ec30c7 | open
EVD-Q-06-comparison | Q | Model portability validation and demonstration | 5 Defend | 40-scale | csv | 2026-10-08T13:51:27Z |  | R2;R5 | model-comparison.md | 5a4971acea3e7d7ceb035d17f2c959d34b61202864fba88ef997b41aaa985b3e | open
EVD-Q-07-manifest-reverification | Q | Model portability validation and demonstration | 5 Defend | 40-scale | json | 2026-10-08T13:51:50Z |  | R2;R5 | stage-q-gate.md; EVIDENCE-INDEX.md | 16fa19c6acfce1e404efcc596f3ca6271f01fdc064369e0ff3e2176b073bf557 | open
EVD-Q-03-demo-rehearsal | Q | Model portability validation and demonstration | 5 Defend | 42-executive | txt | 2026-10-08T12:12:28Z |  | R2;R5 | demo-day-script.md | 4d74a7e8920cbe67c5729cea0654984e84e1980bb9cf95ac3ed6c0f00f2d0be2 | open
EVD-Q-03-rehearsal-script | Q | Model portability validation and demonstration | 5 Defend | 42-executive | sh | 2026-10-08T12:12:28Z |  | R2;R5 | demo-day-script.md | 0b5366ba424272f5f658e48bd9bf195e0a523b5989067c1d24c2278c9606866b | open
EVD-R-03-manifest-verification | R | Executive defence, as-built PRD, production evidence pack | 5 Defend | 42-executive | json | 2026-10-08T12:29:03Z |  | R5 | final-gate.md | 067f226daad1e9de98d1631b12e6699c79e901256545e34efeb138aa2d8c4b1c | open
EVD-R-03-verify-manifests | R | Executive defence, as-built PRD, production evidence pack | 5 Defend | 42-executive | py | 2026-10-08T12:29:03Z |  | R5 | final-gate.md | 83aa911e01ab3607b99199cd97b7b602cdfa265c279e4e9572c2cbd981c3081c | open
EVD-S-01-coverage-matrix | S | Rubric traceability (Runbook 03) | 6 Close-out | 43-rubric-traceability | csv | 2026-10-08T16:04:58Z |  | R5 | docs/43-rubric-traceability/rubric-coverage-matrix.md | eec00684c109d6134a28f5a467f5271c3962ad0afeb39c79d72130e6658693c3 | open
EVD-S-02-finding-rubric-map | S | Rubric traceability (Runbook 03) | 6 Close-out | 43-rubric-traceability | csv | 2026-10-08T16:04:58Z |  | R5 | docs/43-rubric-traceability/finding-rubric-map.md | 9063a0376f7b9fce819b62f3a81e60b7b18f3f9e274685a686d92a7b6065d9c6 | open
EVD-S-01-gen-matrix | S | Rubric traceability (Runbook 03) | 6 Close-out | 43-rubric-traceability | py | 2026-10-08T16:04:58Z |  | R5 | rubric-coverage-matrix.md; blocker-status.md | f3d88b4994810c4527d58994af8eccbece61267cc15089d0d7a2b6ee937061ea | open
EVD-S-01-matrix-rows | S | Rubric traceability (Runbook 03) | 6 Close-out | 43-rubric-traceability | py | 2026-10-08T16:04:58Z |  | R5 | rubric-coverage-matrix.md; blocker-status.md | 7f9f7902f12e89c653b519f7c4e8e69323fa162b44e15b90aed515fc4ade3cd3 | open
EVD-S-02-gen-blockers-and-map | S | Rubric traceability (Runbook 03) | 6 Close-out | 43-rubric-traceability | py | 2026-10-08T16:04:58Z |  | R5 | rubric-coverage-matrix.md; blocker-status.md | 9aa6e49ddeb01f90114c789536e9cb812afac961e69e24e4ac78b84bc0344677 | open
EVD-S-03-finding-evidence-links | S | Rubric traceability (Runbook 03) | 6 Close-out | 43-rubric-traceability | csv | 2026-10-08T16:05:38Z |  | R5 | evidence/EVIDENCE-INDEX.csv; docs/43-rubric-traceability/evidence-index-notes.md | f8d1b2933a86b41c7ed2429309031eefc697d5af4deb1b56411947a05b013128 | open
EVD-S-04-verification | S | Rubric traceability (Runbook 03) | 6 Close-out | 43-rubric-traceability | json | 2026-10-08T16:06:55Z |  | R5 | docs/43-rubric-traceability/verification.md | 5158251708ef62a5dbdeb31588c3ab0fdf99cbb36417d6ec0cf103586c2413d5 | open
EVD-S-04-verify-r3 | S | Rubric traceability (Runbook 03) | 6 Close-out | 43-rubric-traceability | py | 2026-10-08T16:06:55Z |  | R5 | docs/43-rubric-traceability/verification.md | 80c77f151c8279919c1bdab988b4645c12a9db8b72011141cddbafa6ee2f3878 | open
EVD-S-04-gen-index | S | Rubric traceability (Runbook 03) | 6 Close-out | 43-rubric-traceability | py | 2026-10-08T16:06:55Z |  | R5 | docs/43-rubric-traceability/verification.md | bdaee290ccfc2e652164f37360ea4505914fc6eb44b0e4d4c808b10606b3b296 | open
EVD-T-01-operator-decision-record | T | Open questions and decisions (Runbook 04) | 6 Close-out | 44-decisions | json | 2026-10-08T16:33:03Z |  | R3 | docs/44-decisions/open-questions-register-v2.md; runbook/04-OPEN-QUESTIONS-FINAL-REVISION.md | 63041f322b3c570695e6a8eb389c13fef56e24b79a6af51ef8d014df58d0f9ba | open

## Findings
62 baseline findings and their final disposition
Source: evidence/13-traceability/EVD-F-04b-finding-disposition-final.csv; rubric criteria from EVD-S-02. S1 = most severe.
Finding | Severity | Title | Final disposition | Rubric criteria | Evidence | Owner role | Note
F-01 | S1 | The repository is not under version control | FIXED | R1;R3 | evidence/00-preflight/EVD-A-01-tag-verification.txt | n/a
F-02 | S2 | The documented test command cannot run | FIXED | R1;R4 | evidence/15-modernization/EVD-H-02-quickstart-after.txt vs evidence/07-repo-assessment/EVD-C-02-quickstart-transcript.txt; CI run 2 | n/a
F-03 | S3 | The documented run command is wrong | FIXED | R1 | README Quick Start; EVD-H-02 | n/a
F-04 | S2 | No dependency lockfile for either stack | FIXED | R2 | hash-pinned requirements.txt/requirements-dev.txt (--require-hashes in CI run 2); apps/web/package-lock.json (lockfileVersion 3) | Web lead (UNRESOLVED) | npm audit not run (DEBT-14)
F-05 | S2 | Documentation claims a portal that does not exist | CHANGED | R1;R4 | README corrected; thin static operations view; tests/test_ops_view.py; EVD-J-04-browser-e2e.json | Product owner (UNRESOLVED) | Angular portal NOT built; OQ-06 ruling
F-06 | S3 | The frontend lint gate is "lint": "echo scaffold" — a no-op that reports success. | PARTIAL | R2 | apps/web/package.json lint now runs scripts/lint-scaffold.mjs instead of echo | Web lead (UNRESOLVED) | a scaffold check, not a framework linter; no frontend build exists (DEBT-10)
F-07 | S2 | No containerisation or environment definition: no Dockerfile, no compose file, no devconta | PARTIAL | R2 | Dockerfile, docker-compose.yml, entrypoint; EVD-P-02 exercises | Platform lead (UNRESOLVED) | image never built in this workspace (DEBT-06)
F-08 | S2 | No change-control surface: no CONTRIBUTING.md, no PR template, no CODEOWNERS, no branch-pr | PARTIAL | R3 | CODEOWNERS, PR template, CONTRIBUTING.md, SECURITY.md; GitHub API 2026-10-08: main branch not protected (HTTP 404) | Repository owner (UNRESOLVED) | branch protection needs admin action
F-09 | S1 | A database password is hardcoded in source | FIXED-IN-TREE | R3 | EVD-H-03-secret-scan.json (0 findings); tests/test_secret_scan.py | Repository owner (UNRESOLVED) | value still in git history and in public repo: see F-09 history row DEBT-11, RA-07
F-10 | S1 | .env.example ships a complete DSN with embedded credentials: postgresql://app_shared:Welco | FIXED-IN-TREE | R3 | EVD-H-03; scripts/secret_scan.py | Repository owner (UNRESOLVED) | history residual (DEBT-11)
F-11 | S2 | .env.example ships AI_GATEWAY_KEY=sk-workshop-hardcoded-example — a key-shaped literal in | FIXED-IN-TREE | R3 | EVD-H-03 | Repository owner (UNRESOLVED) | history residual (DEBT-11)
F-12 | S1 | .env.example ships OT_VENDOR_TOKEN=replace-me-but-currently-shared — the comment itself do | FIXED-IN-TREE | R3 | EVD-H-03 | Repository owner (UNRESOLVED) | history residual (DEBT-11)
F-13 | S2 | .env.example sets LOG_LEVEL=DEBUG as the default, meaning verbose logging of operational p | FIXED | R3 | tests/test_config.py | n/a
F-14 | S1 | No secret detection anywhere: no scanner in CI, no pre-commit hooks, no rotation policy | FIXED | R3 | scripts/secret_scan.py in CI run 2; tests/test_secret_scan.py | n/a
F-15 | S2 | The IaC emits a credential artifact | FIXED | R3 | tests/test_config.py; infra/terraform/main.tf emits no credential | n/a
F-16 | S2 | No encryption posture exists: no TLS configuration, no at-rest statement, no key managemen | DEFERRED | R3 | GAP-01; privacy-impact-assessment.md | Platform lead (UNRESOLVED) | TLS and at-rest encryption belong to an undecided platform
F-17 | S1 | Authorisation is a client-supplied HTTP header | FIXED | R3 | tests/test_identity_policy.py; EVD-H-04; EVD-L-03 RT-02/RT-11 baseline succeed, v2 fail | n/a
F-18 | S1 | The role check is a flat five-element allow-list with no resource, tenant, facility, purpo | FIXED | R3 | policy engine + access-semantics.yaml; EVD-H-04 allow/deny matrix | n/a | scope narrowing by hub/fleet not enforceable (DEBT-05)
F-19 | S1 | The allow-list contains a persona from another domain | FIXED | R1;R3 | characterization AB-04; RT-03 | n/a
F-20 | S1 | The AI endpoint has no authorisation check whatsoever | FIXED | R3 | characterization AB-06; RT-01 | n/a
F-21 | S1 | policy/opa/access.rego is role-only (admin → all, operator → read) | FIXED | R3 | policy/opa/access.rego generated from access-semantics; opa check and opa test green in CI run 2 | n/a | engine in request path is Python; OPA parity test skipped locally, run in CI
F-22 | S1 | Prompt injection surface | FIXED | R3 | tests/test_ai_gateway.py; RT-07 baseline succeeds, v2 fails | n/a | tested with constructed payloads only (F-60)
F-23 | S2 | Using str.format() on attacker-influenceable content is additionally a format-string injec | FIXED | R3 | tests/test_ai_gateway.py (no str.format on data) | n/a
F-24 | S1 | The system self-reports that no guardrail exists: the response literal is "guardrail_statu | FIXED | R3 | characterization AB-07; RT-09 | n/a | guardrail is deterministic; untested against a real model
F-25 | S1 | No output schema validation | FIXED | R3 | schema validation in gateway; EVD-H-07 | n/a
F-26 | S1 | No human approval gate | FIXED | R3 | tests/test_human_control.py (9); RT-10 | n/a | self-approval still possible (HC-R-01, RA-04)
F-27 | S1 | Model provenance is a module constant (MODEL_VERSION = "local-sim-v1") | FIXED | R3 | prompts.lock.json, models.lock.json, registry; tests/test_prompt_lock.py | n/a
F-28 | S2 | Token accounting is fabricated: token_estimate = len(prompt.split()) * 2 | PARTIAL | R2;R3 | tokens are estimates; EVD-H-07 | AI lead (UNRESOLVED) | real counts only with a real model
F-29 | S1 | The AI output is not derived from the record's meaning | PARTIAL | R1;R4 | deterministic summary from allow-listed facts (AB-08) | AI lead (UNRESOLVED) | ETA Prediction, Route Optimization, Exception Copilot remain NOT IMPLEMENTED; answer quality unproven
F-30 | S1 | Cross-entity primary-key collision | FIXED | R1;R2 | tests/test_record_lookup.py; RT-06 | n/a | REC-0001 rejected by key pattern; owner intent OQ-15 unresolved
F-31 | S1 | Record lookup scans every column, not the key | FIXED | R2 | tests/test_record_lookup.py; RT-04 | n/a
F-32 | S1 | A missed lookup silently returns the wrong record | FIXED | R1;R2 | characterization + 404/422; RT-05 | n/a
F-33 | S2 | Three duplicate business keys in every dataset, at a consistent *-00004, *-00013, *-00019 | FIXED | R1 | tests/test_etl_quarantine.py; EVD-H-06 | n/a | quarantined to data/quarantine; fixture untouched
F-34 | S2 | One fully-blank mandatory row in every dataset — every non-key column empty (10 blank colu | FIXED | R1 | tests/test_etl_quarantine.py | n/a
F-35 | S2 | One impossible timestamp per timestamped dataset: 1900-01-01T00:00:00 in shipments.promise | FIXED | R1 | tests/test_etl_quarantine.py | n/a
F-36 | S2 | tracking_events.confidence spans 0.001–1.42 | FIXED | R1;R2 | ETL validation rules; EVD-H-06 | n/a
F-37 | S1 | No semantic layer: categorical columns are polluted with workflow-status vocabulary | FIXED | R1;R2 | semantic-layer/ (status-taxonomy, enum-violations.md); enforced in ETL | n/a | enum meaning of 14 tokens is inferred, not owner-confirmed
F-38 | S2 | Referential integrity is unenforced | FIXED | R1;R2 | ETL orphan and duplicate-booking checks; EVD-H-06 | n/a
F-39 | S1 | A retry storm is already visible in the data | FIXED | R2 | retry ceiling 5 and idempotency key; tests/test_carrier_saga.py; EVD-J-05 | n/a | against a simulated carrier only
F-40 | S2 | ETL counts defects and discards them | FIXED | R2 | tests/characterization; non-zero exit above threshold; EVD-H-06 | n/a
F-41 | S2 | The ETL has no run identifier, watermark or idempotency key | FIXED | R2 | run_id and load_id in ETL report | n/a
F-42 | S1 | About one third of the event stream cannot be correlated | PARTIAL | R1;R3 | new events carry correlation id (tests/test_audit_chain.py); N2 reconstruction | Data owner (UNRESOLVED) | historical events.jsonl unchanged: 1,992 of 3,000 unusable (D-012)
F-43 | S1 | The audit event records only ts, action and details | FIXED | R3 | characterization AB-09; EVD-N-02 field coverage 10/10 | n/a
F-44 | S1 | The audit sink is a local file written by the application itself — <repo>/logs/audit.log, | PARTIAL | R3 | hash-chained audit; /audit/verify; tamper test | Platform lead (UNRESOLVED) | sink still a local file written by the audited process (DEBT-04)
F-45 | S2 | datetime.utcnow() yields a naive timestamp with no timezone marker | FIXED | R3 | timezone-aware UTC timestamps in the v2 chain; tests/test_audit_chain.py | n/a | legacy shim apps/api/services/audit.py still calls utcnow(); documented as not called by the API (DEBT-12)
F-46 | S1 | No tracing, no metrics, no SLOs, no dashboards-as-code, no alerting, no error budget | PARTIAL | R3 | /ready, /metrics, 3 dashboards, 15 alerts as code (EVD-N-01: 31 rules, 0 failed) | SRE (UNRESOLVED) | no traces; no collector has ever run; no alert recipients
F-47 | S2 | CI executes commands but produces no evidence | PARTIAL | R2;R3 | CI ran on GitHub (runs 37774970836 failed, 37776230304 green on 3.11 and 3.14): lint, types, secret scan, coverage, OPA, evidence artifacts | Repository owner (UNRESOLVED) | CI has no SAST or dependency-audit or SBOM step (run locally in M1)
F-48 | S2 | The Terraform is a local_file resource with no provider, no backend, no state management a | DEFERRED | R2 | infra/terraform/main.tf emits no credential but provisions nothing | Platform lead (UNRESOLVED) | M-X2 NOT MET
F-49 | S2 | supply-chain/dependency-risk-register.md correctly names "no SBOM" and "no provenance" as | FIXED | R2;R3 | EVD-M-01 SBOM runtime 21 and dev 58 components, pip-audit 0, bandit 12 triaged | n/a | SBOM not produced by CI
F-50 | S2 | The API contract omits both business endpoints | FIXED | R2;R4 | OpenAPI drift test tests/test_contract_ops.py; sanity_check openapi_route_diff clean | n/a
F-51 | S2 | The characterization test characterises nothing | FIXED | R1 | tests/characterization (11 behaviours); EVD-C-08 | n/a
F-52 | S2 | tests/playwright/operations.spec.ts asserts that body is visible against an application th | CHANGED | R4 | Playwright spec replaced in effect by tests/test_ops_view.py and EVD-J-04 Chromium run | Dev lead (UNRESOLVED) | spec not run with npx (TEVV-R-07)
F-53 | S2 | A known architectural divergence is documented and unmanaged | FIXED | R1;R2 | docs/10-architecture/adrs/ADR-0002 supersedes ADR-0001 | n/a
F-54 | S2 | Data remediation will break the repository's own contract test | FIXED | R1;R2 | curated layer; fixture immutable; make smoke original assertions kept | n/a
F-55 | S3 | scripts/sanity_check.py hard-requires the paths docs/transformation-roadmap.md, docs/domai | FIXED | R2 | sanity_check required paths preserved | n/a
F-56 | S2 | The incident runbook declares itself *"intentionally incomplete"* | FIXED | R3 | docs/29-incident-bcdr (13 docs) | n/a | tabletop was one author (TT-1); no on-call exists (GAP-06)
F-57 | S2 | No business KPI data exists | PARTIAL | R1;R4 | baseline KPI proxies frozen (C1); after-KPIs unchanged (O1) | Business sponsor (UNRESOLVED) | no business KPI exists; verified monetary benefit nil
F-58 | S3 | ai_invocations.csv also has an orphan shipment reference (REC-0001 row); not in the origin | FIXED | R1 | tests/test_etl_quarantine.py | n/a
F-59 | S3 | 171 of 351 shipments have actual weight above declared weight (meaning unknown) | ACCEPTED-PROPOSED | R1 | flagged in ETL; DEBT-09 | Business owner (UNRESOLVED) | approver: NONE; 171 rows actual>declared, meaning unknown
F-60 | S2 | data/README.md claims untrusted text payloads for prompt-injection testing; no free-text f | FIXED | R1;R3 | data/README.md corrected; tests use constructed payloads | n/a
F-61 | S3 | routes.weather_risk holds numeric 1.42 in a categorical field | FIXED | R1;R2 | ETL enum rule | n/a
F-62 | S3 | Every dataset has one malformed key *-BAD1 | FIXED | R1;R2 | tests/test_etl_quarantine.py | n/a

## Red Team
Red team: the same 12 attacks against Repo 1.0 and Repo 2.0
Source: evidence/26-tevv/EVD-L-03-redteam-baseline.json and EVD-L-03-redteam-v2.json. Run by the builder, not an independent team.
Attack | Finding | Goal | Repo 1.0 HTTP | Repo 1.0 result | Repo 2.0 HTTP | Repo 2.0 result
RT-01 | F-20 | invoke the AI endpoint with no identity | 200 | Succeeded | 401 | Failed
RT-02 | F-17 | self-assert an admin role with a header | 200 | Succeeded | 401 | Failed
RT-03 | F-19 | use a persona from another domain | 200 | Succeeded | 401 | Failed
RT-04 | F-31 | look up a record through a non-key column | 200 | Succeeded | 422 | Failed
RT-05 | F-32 | ask for a record that does not exist | 200 | Succeeded | 422 | Failed
RT-06 | F-30 | reach the planted colliding key | 200 | Succeeded | 422 | Failed
RT-07 | F-22 | get attacker text reflected through the AI output | 200 | Succeeded | 422 | Failed
RT-08 | F-22 | get attacker text from a categorical field into the AI output | 200 | Failed | 200 | Failed
RT-09 | F-24 | find the guardrail switched off | 200 | Succeeded | 200 | Failed
RT-10 | F-26 | action a suggestion without any human approval step | 404 | Failed | 401 | Failed
RT-11 | F-17 | forge a token (alg none, role admin) | 200 | Succeeded | 401 | Failed
RT-12 | F-46/NFR | exhaust the AI endpoint without a limit | 200 | Succeeded | 429 | Failed
|  | Attacks that succeeded |  | 10 |  | 0

## KPIs
KPIs K1 to K10: before and after
Source: docs/34-after-kpis/after-intervention-kpi-sheet.md; evidence/34-after-kpis/EVD-O-01-after-kpis.json. K9 re-run on 2026-10-08. None of this is a business outcome.
KPI | Measure | Baseline | After | Equal? | Reading
K1 | Latency p50 / p95 / max (ms) | 1667 / 13709 / 14999 | 1667 / 13709 / 14999 | yes | A column of the static fixture, not a service measurement
K2 | Cost per event | 2.2451 | 2.2451 | yes | Static fixture
K3 | Severe-event share | 39.6% | 39.6% | yes | Static fixture
K4 | Correlation completeness (source stream) | 33.6% | 33.6% | yes | The producer still emits no id (F-42)
K5 | Declared AI tokens | 904,432 | 904,432 | yes | Declared by the dataset
K6 | Retries min / mean / max | 51 / 2508.5 / 4995 | 51 / 2508.5 / 4995 | yes | Static fixture
K7 | Duplicate keys (raw layer) | 18 | 18 | yes | Seeded defects stay in the raw files; quarantined downstream
K8 | Incomplete rows (raw layer) | 6 | 6 | yes | Seeded defects stay in the raw files; quarantined downstream
K9 | Tests | 3 of 3 pass (0 collected without httpx) | 181 passed, 7 expected xfail (170 at Stage O) | n/a | Engineering health, not operations
K10 | Coverage | 45% | 97% (apps and etl) | n/a | Engineering health

## Rubric Coverage
Rubric coverage: sub-dimensions per criterion
Source: docs/43-rubric-traceability/readiness-assessment.md (counts) and EVD-S-01-coverage-matrix.csv (rows below). Index = (MET + 0.5 x PARTIAL) / sub-dimensions. It measures evidence completeness, not marks.
Criterion | Name | Marks | MET | PARTIAL | NOT MET | BLOCKED | Sub-dimensions | Coverage index
R1 | As-Is understanding | 20 | 6 | 1 | 0 | 0 | 7 | 0.92857
R2 | Repo 2.0 design | 25 | 5 | 4 | 0 | 0 | 9 | 0.77778
R3 | Governance, risk, security | 20 | 5 | 2 | 1 | 1 | 9 | 0.66667
R4 | PRD and working application | 25 | 4 | 1 | 0 | 1 | 6 | 0.75
R5 | Presentation and defence | 10 | 4 | 1 | 0 | 0 | 5 | 0.9
Total |  | 100 | 24 | 9 | 1 | 2 | 36
File-level matrix rows (each row: a sub-dimension, its status, and one file that evidences it)
Criterion | Sub-dimension | Status | Evidence file | SHA-256
R1 | Understanding Repo 1.0 | MET | docs/00-preflight/discovery/system-landscape.md | c9e01c93ab63e0158e6c2d8055095cf5fadaef9cb9755f927fc02617627bead3
R1 | Understanding Repo 1.0 | MET | docs/00-preflight/discovery/security-observability-overview.md | 2a4de67330bd63114e7baf006e29a48538dc895574ae34dae41fd034de1bbb98
R1 | Understanding Repo 1.0 | MET | docs/00-preflight/discovery/assumptions-unknowns.md | c6d6d21ccb0e9f84805b8b48466e1c3f91ca5144f69f1afde3515ce52e1deb13
R1 | Understanding Repo 1.0 | MET | docs/00-preflight/discovery/test-overview.md | 8f6427f52af572ae1148000707e5a3037a0f997007f15aaf3aaaa0b21de012fe
R1 | Understanding Repo 1.0 | MET | docs/00-preflight/discovery/environment-snapshot.md | 3183093fa1a009c5479a572c026ac4d732cb0234b226424c4e2aff9587aa9c44
R1 | Understanding Repo 1.0 | MET | docs/05-current-state/manual-handoffs.md | 3bff471d8b925e062cebdd95b1a1d539fc50488674b25a3b66f4caccd305782e
R1 | Understanding Repo 1.0 | MET | docs/05-current-state/brownfield-inventory.md | be7a4e9b6064139d8ae3b2ac8722846843abc5208983556123515f0ab0115815
R1 | Understanding Repo 1.0 | MET | docs/05-current-state/system-landscape.md | ebaaf6e1ffc7aae411cfd2410f0cf2c9396ff767e342d38b3be843fdbce4d62a
R1 | Understanding Repo 1.0 | MET | docs/05-current-state/current-state-summary.md | af98be49a093cacc8c85a9d6e50631553d06fc225fe3e2d8e613fa266ef7ab8b
R1 | Understanding Repo 1.0 | MET | docs/05-current-state/dependency-hotspots.md | 0676ad01ad5346459505e66bb23967bbf5e4e69fcf3b77b08098796049a3cde2
R1 | Understanding Repo 1.0 | MET | docs/07-repo-assessment/repo-assessment.md | 0b1f2f8ad6ab41854913dba2a45588ef81cc428eb48946c30cd24a5fbec08b9d
R1 | Identifying gaps and inconsistencies | MET | evidence/04-baseline-kpis/EVD-C-05-data-profile.json | 6314f00faa1df6c781714c3be2e946cae1b323858f1b435868989a8f4dced202
R1 | Technical debt | MET | docs/07-repo-assessment/technical-debt-register.md | 8a0f91a96a938bc28aeaee98d10bbc8e0d78a53938da02041c9d8faf1e16dff0
R1 | Technical debt | MET | docs/07-repo-assessment/legacy-pattern-register.md | edb42201376a2e648486c82a81e05140801996a44727ddb9d66e4a218fa83e87
R1 | Technical debt | MET | docs/07-repo-assessment/partial-migration-register.md | 894dc4bb561387ca6b65b8c22cc3e879c253afcdadf65acb5981cf4542da79f4
R1 | Risk identification | MET | docs/00-preflight/discovery/initial-risk-register.md | f22c36ad03bd6842974df564c2e98bc95a1c003c8944476cac44a026117d2e21
R1 | Risk identification | MET | docs/06-root-cause/evidence-confidence-matrix.md | 36ee9b249afcffbc3619c4c422371f1c75be36e8e5fae408d97a34ab712986d9
R1 | Behavioural baseline | MET | evidence/07-repo-assessment/EVD-C-02-quickstart-transcript.txt | 74e85bd8cec2ade87fc4ccf8a95b40552928010bfd689e761b21868fdf541581
R1 | Behavioural baseline | MET | evidence/07-repo-assessment/EVD-C-03-junit.xml | 1d96dc44eb81588a1155ba4566d8d87ab7ef22d62ba21b803f7835d3926ca8da
R1 | Behavioural baseline | MET | evidence/07-repo-assessment/EVD-C-03-coverage.xml | 85210479df1b835c07459cca3a26494695ede817d7399bc85133811e92b607e8
R1 | Behavioural baseline | MET | evidence/07-repo-assessment/EVD-C-03-transcript.txt | e00e2c43b291f1a06e7144f029873e2b4422672353800328fc2534d30060b743
R1 | Behavioural baseline | MET | evidence/07-repo-assessment/EVD-C-08-characterization-junit.xml | b35040581e79ee0e1b912f8399b855e60ef591ad76c24faa27eb7c0169ffd90e
R1 | Business problem | MET | docs/03-problem-value/problem-statement.md | f580a33f48126b2dd1a853ca7c197f3e6e150601e96f73d6f82b82afe3605544
R1 | Business problem | MET | docs/01-engagement/engagement-go-no-go.md | 13bfaff9cd0f52c433dc808afa7a787b4a0ec78d031b5a2a4fba06f7403f1cae
R1 | Before/after proof | PARTIAL | evidence/16-repo-validation/EVD-H-10-behaviour-diff.csv | c78a8433c06d9266db854f14d8ee3393ff348a4dd42dc5cdd032114fc0c92b58
R1 | Before/after proof | PARTIAL | evidence/31-observability/EVD-N-02-reconstruction.json | 1eed65aa84641d9e7d564b91a99baa04006f1ba05ca26590cdae5a8181e6c241
R1 | Before/after proof | PARTIAL | docs/35-value-leakage/kpi-variance-table.md | dfe3b390918a9e3f07373702c4416a606c748dd502ecb28ef4907d95e49aa106
R2 | Improved architecture | MET | docs/10-architecture/target-architecture.md | 0e1d441ad4067f5438fa3097354904ae66f2963b5ad73a55645661aba60abf2e
R2 | Improved architecture | MET | docs/10-architecture/adrs/ADR-0002-supersede-0001-partial-modernization.md | 1206a3152b408f7daa856f03bdaf7b656fe5a73ab6ad70d35602d67f415622a0
R2 | Improved architecture | MET | docs/10-architecture/adrs/ADR-0003-target-runtime-and-dependencies.md | 944aa4ec55d4b062bd8f3568c02d872a2f833367aea60ec09746ba4f81dabe9b
R2 | Improved architecture | MET | docs/10-architecture/adrs/ADR-0004-identity-and-authentication.md | e4486a7ae1af2411891cb837ab0cb4cbf60061b651a307ae59edddb25d19ebc3
R2 | Improved architecture | MET | docs/10-architecture/adrs/ADR-0005-authorisation-policy-as-code.md | 0e8cb35810a4fe4227f00398a2d68f13e4ffc9f4dd15efe11ae00a2a3651a1d5
R2 | Improved architecture | MET | docs/10-architecture/adrs/ADR-0006-data-layer-and-quarantine.md | 3391a55d265dd2a0918db91a61b03a0ff9fe9da96f05527316757c309bbebb17
R2 | Improved architecture | MET | docs/10-architecture/adrs/ADR-0007-ai-gateway-boundary.md | 6e48c75b58e10398075b0c39c8f90a645c95a53a6d84b03c1416288a46a115ec
R2 | Improved architecture | MET | docs/10-architecture/adrs/ADR-0008-audit-and-correlation.md | b79b95f86b3e9ffda9d04328c407b3ca48a3d8e8736ba9e72fa512372f56ef5f
R2 | Improved architecture | MET | docs/10-architecture/adrs/ADR-0009-platform-neutral-deployment.md | 8e92250e0fa79e1ce0e4e2880fc102df3060e551fbd004f3bdd15f678aeedbba
R2 | Improved architecture | MET | docs/10-architecture/adrs/ADR-0010-observability.md | bed0a9089f8dded930fa7578a865e51c4f1a2740dd4763d23afe6d7fa94e94b5
R2 | Improved architecture | MET | 07-logistics-shipment-fleet-routing-ops/docs/ADR/0001-partial-modernization.md | 03daaa1c3273ce2b27e6a87c86b3f388cbdc9da5e4597353e6d4f99d7dd43ba1
R2 | AI workflow | MET | docs/19-intelligence/prompt-registry.md | 3125bbcf7629941e9fb9a904c26e7bf9a7a54a87b0ac07798c7da8206d38d50f
R2 | AI workflow | MET | docs/20-application/deterministic-ai-boundary.md | a9cd8bfd5d8285fbc934e8ff583f79eef6b38cf924bca6e1f22c7c50a878954e
R2 | AI workflow | MET | evidence/15-modernization/EVD-H-07-ai-gateway-results.json | 38fe45eb845bc0d5c3aebbc45d155f9d0a2997ee758cf39c497312d245b1aec6
R2 | AI workflow | MET | docs/19-intelligence/quality-latency-cost-results.md | 96027379bb6de316dd55d53b5ca35489a8de32f3001710dacb8fae70422882cf
R2 | Data / evidence design | MET | docs/11-data-context/data-contracts.md | 78fa0ea4c7e0648be1dd7158466d1484862f792653379f7e369a7782fa5cf921
R2 | Data / evidence design | MET | docs/21-integration/data-contracts.md | 3f8403da563e66f63c7e00cc0bfda233be2aeb9add01b3c7d41d1ea792193a51
R2 | Data / evidence design | MET | docs/11-data-context/data-quality-rules.md | 8259d91d6ee24d0b50bfee2c001b41784a9db9cb2890da2390497bd728971485
R2 | Data / evidence design | MET | docs/11-data-context/provenance-policy.md | eee09cf8efdb90592ed33946e88d6500d299f1c8fbc0b39ee814ccec2860e766
R2 | Data / evidence design | MET | semantic-layer/README.md | b38fc745d2ddfff755cbb7b92fac68b48d47ea2f7c4b6bae45b757a6de406ec2
R2 | Data / evidence design | MET | semantic-layer/entities.yaml | 3d715cf088893a523d37b75fe8f917e9657f495c621478f61d718ce5f51ef8f3
R2 | Data / evidence design | MET | semantic-layer/access-semantics.yaml | 5082131647358b428f48d7122b8f043150a768a76b32d90031ce89e1540eef84
R2 | Data / evidence design | MET | semantic-layer/business-rules.yaml | e33b1d31d398865207a92903354eebc4ce7b78410eb0125d73543738260e900f
R2 | Data / evidence design | MET | semantic-layer/ai-context-policy.yaml | b9e7285d1011e6cdad6b3983b83a28828408fd501dfeeb3b7555ca2a8d7ff214
R2 | Decisioning | PARTIAL | semantic-layer/access-semantics.yaml | 5082131647358b428f48d7122b8f043150a768a76b32d90031ce89e1540eef84
R2 | Decisioning | PARTIAL | 07-logistics-shipment-fleet-routing-ops/policy/opa/access.rego | b133c752e6d05db6470ffbb6c6c2591b88eb72226f0974784f02e9ddb6d96b82
R2 | Decisioning | PARTIAL | 07-logistics-shipment-fleet-routing-ops/policy/opa/access_test.rego | 7952431293519c447a5e9a57f8a19740cbbdc98135e617a522c9d5c32cdeca63
R2 | Decisioning | PARTIAL | docs/23-human-control/autonomy-matrix.md | b72434cd88a01d18138efaed4861bacf145d003ae5ae3ba24972f82694448b49
R2 | Controls | MET | evidence/15-modernization/EVD-H-03-secret-scan.json | 9be399823ccf9be244917852a3f19b4ee67b5e5d2c813fae5b7f4c4fd20c4dab
R2 | Controls | MET | evidence/15-modernization/EVD-H-04-negative-access-tests.txt | c724516d79f2e15cce8017516c2a82a30c2eb663c4fe08b5cc83b181213eb2eb
R2 | Controls | MET | evidence/15-modernization/EVD-H-04-policy-allow-deny-matrix.csv | f838baffa93da9043a972b23f70f36a84f9442848d2805d4a2d029f4a96ad25a
R2 | Controls | MET | evidence/16-repo-validation/EVD-H-09-smoke.txt | e3d44aec2bed164620555f0b9ae4deafa1d4a35c62eecdf6e14cb4417681b80f
R2 | Controls | MET | docs/27-hardening/sbom-summary.md | 3516f9766a1da2663b8817f1ab95a14436d1dcc324ad8a969919c118130625d5
R2 | Resilience | PARTIAL | docs/28-resilience/resilience-architecture.md | 06f3e9ef4a9d1a570db27744bd5dd0614453e9ada92a3c15bb4a4907df772782
R2 | Resilience | PARTIAL | docs/28-resilience/ai-disabled-mode.md | 6661f44edfded7dbb285edaf7db3d6dc3f6e8abe9d6113d1aaf60b142c27cb2e
R2 | Resilience | PARTIAL | evidence/28-resilience/EVD-M-03-resilience-tests-after-drills.txt | 9c509bda36ef6a69faa52ede33666646c59e27907c5e1c8e1027767115c4b8a8
R2 | Reproducibility | PARTIAL | evidence/15-modernization/EVD-H-02-quickstart-after.txt | 253337ce0f1b3e20361e42b612628b9447c629ce33633ea48bd88696d8310c70
R2 | Reproducibility | PARTIAL | 07-logistics-shipment-fleet-routing-ops/Dockerfile | cb01dde9a937699b72ae3328e812a8a527d5a45cfc1f5de4e82d0d4af7a98481
R2 | Delivery pipeline | MET | evidence/15-modernization/EVD-H-01-pipeline-run.txt | 943f500b2da991e6bfcf1bba9740cfe8839bde806197ba9ac03d98cad007bd2b
R2 | Delivery pipeline | MET | docs/16-repo-validation/repo-quality-gate.md | 176ced5405566c24609c0f26284220f011af7ad652a06b68e441a82e50c9e1d6
R2 | Portability | PARTIAL | evidence/40-scale/EVD-Q-01-preregistration.json | d050b98fe3a419f360f48be9edb646e952ccd3d08488cd5639d41556da875014
R2 | Portability | PARTIAL | evidence/40-scale/EVD-Q-02-comparison.csv | 25b4aaddc9c676a3d13545292d79e791d6b3296d750047d7eae28ed004b32656
R3 | Human oversight | MET | docs/23-human-control/autonomy-matrix.md | b72434cd88a01d18138efaed4861bacf145d003ae5ae3ba24972f82694448b49
R3 | Human oversight | MET | docs/23-human-control/approval-gates.md | 0c377d65e82a03ce1b751f0104f9f2f161d72c94a49907d6e1838d3429864392
R3 | Human oversight | MET | docs/23-human-control/human-control-test-results.md | b8690608e712597ce34312f45ec4819d0660ac21935de14d037c6cc901a60d83
R3 | Explainability | MET | docs/19-intelligence/prompt-registry.md | 3125bbcf7629941e9fb9a904c26e7bf9a7a54a87b0ac07798c7da8206d38d50f
R3 | Explainability | MET | docs/19-intelligence/grounding-results.md | fe47a9175ec81c84e3754cb1c0bede8e902b4e2e10addc62c467f3724afadd09
R3 | Explainability | MET | docs/31-observability/ai-telemetry-spec.md | da032038d4cf7922333e1adf9bffa5ccb0e5a7f7fa65fb29cec126db931b10c6
R3 | Auditability | MET | evidence/15-modernization/EVD-H-08-trace-sample.json | 5b79ef4cf9cc76f6b5d6e39dd9300d709b0e7633f933e1c21029adc4b07a1e88
R3 | Auditability | MET | evidence/31-observability/EVD-N-02-reconstruction.json | 1eed65aa84641d9e7d564b91a99baa04006f1ba05ca26590cdae5a8181e6c241
R3 | Auditability | MET | docs/25-governance/audit-evidence-index.md | b955248600c2dadf55bc687a3a50ce3be69c35d3830750f1382bff1bdc164e35
R3 | Risk controls | NOT MET | docs/24-security-privacy/security-control-matrix.md | 40132faa0d3dc86904f18d83d5e0d8c8fefe8cfcedd5582223f8554be94db092
R3 | Risk controls | NOT MET | docs/24-security-privacy/residual-security-risks.md | f4019e852133fbb5f05db701150dab683253a411c790a839c4c53107cb5fa369
R3 | Risk controls | NOT MET | docs/26-tevv/residual-tevv-risks.md | a4729cd1dcf1b844aba5ccdfe68883806348c3f614f71faa2e352efb70fe5abf
R3 | Security | MET | evidence/26-tevv/EVD-L-03-redteam-v2.json | b6f65533d6d71145d1d98da52ee5886590871091c704bc514e07984327d03356
R3 | Security | MET | evidence/26-tevv/EVD-L-03-redteam-baseline.json | 690911c90695c307f620ac56aec88e8d0da9732b4f6405dbf9c381e38df9213f
R3 | Compliance | BLOCKED | docs/25-governance/compliance-obligations.md | 4a737b679b823d453d80db8283380a0e9e07b5e9de62ab91d3c23949dba3ae61
R3 | Compliance | BLOCKED | docs/25-governance/model-card.md | 8f31e69561272ea62376c18d32002a0425c9a9c4d57e383ddc2b98d57eac2339
R3 | Compliance | BLOCKED | docs/25-governance/system-card.md | 7750a7180a6ea60fc2abc5d999a76664a9ca428d84d66ca3e1e0cd42fbd7b558
R3 | Compliance | BLOCKED | docs/25-governance/evidence-retention-policy.md | 89335f68900a46974a87e9a2e295b3eabccf2bf5f172ca1a50d346339c9ed5bc
R3 | Observability | PARTIAL | docs/31-observability/slo-sla-definitions.md | 716903096d4def95eb05ff85564272c13d1a2404841044f51197fce51a3843ed
R3 | Observability | PARTIAL | docs/31-observability/observability-validation.md | 6cb7f4a703daa5f9448f1deef2703402973398b68e958d1a359f210bd31810bb
R3 | Safe AI boundaries | MET | docs/08-ai-qualification/deterministic-vs-ai-boundaries.md | d68db4e1c4d65725540ce87c5f8bffac8ee3587c1075958ed49930819256bbda
R3 | Safe AI boundaries | MET | docs/24-security-privacy/prompt-injection-controls.md | b8f170b83c1fc3bac8935e0ec52e507ec2fe3394d154422d56045aed95c64c40
R3 | Change governance | PARTIAL | evidence/14-transformation/EVD-G-04-authorisation-record.txt | 88f1b4321b2f75114ce9c1a23866a289757ac3f81358180c55b323d15d2e4679
R3 | Change governance | PARTIAL | docs/39-continuous-improvement/controlled-change-process.md | ebd3846262d87fc2f0e9c7d4bf996102f0c6bf240c33d1155d04becc6034dd5c
R3 | Change governance | PARTIAL | .github/CODEOWNERS | 7d15df156f3bb67926e2a9d3b80c4cccc1315e7bd5e9f7457166d203e7c62ac4
R4 | PRD quality | MET | docs/09-initial-prd/initial-prd.md | 0f720473c87dfbceea910344602f3ba928cca6e33baa7d27b716f62e399408af
R4 | PRD quality | MET | docs/17-implementation-prd/implementation-prd.md | c6ea0657f75e58f5c926b3c9ea4034ccbd9d793f09c87462588d236b1e0f89f7
R4 | PRD quality | MET | docs/final-prd/final-as-built-prd.md | 47c277c5ada67241abf2f388a1b10e43c687d532dc0a9bdccd4799e633a23b10
R4 | Requirement traceability | MET | docs/13-traceability/requirements-traceability-matrix.md | 33c1540cf5e9c6eca2ca5193afe8d0c90f0a2b30ab62b6ec37feff89fcd49dca
R4 | Requirement traceability | MET | evidence/13-traceability/EVD-F-04-finding-coverage-matrix.csv | 055a52f15d9daafa8d76bc642da760ea3a404790ac7d0fcefbb9f76ba1016821
R4 | Requirement traceability | MET | docs/final-prd/requirement-disposition-matrix.md | a7619159ed8df89b36c963fb72e36079335c690a7daab01164b7e9a5ff4d4678
R4 | Functional implementation | MET | docs/20-application/application-test-summary.md | ca27f76c7731668495e5306be352b1c8106fff67cdb007e43ca38474d6a13d44
R4 | Functional implementation | MET | docs/21-integration/integration-test-results.md | c612abfaa9cda7dfbac234085b3ecfd4a7745aa6fbc95bf1ab9ad12b6487f9a7
R4 | End-to-end workflow | PARTIAL | evidence/31-observability/EVD-N-02-reconstruction.json | 1eed65aa84641d9e7d564b91a99baa04006f1ba05ca26590cdae5a8181e6c241
R4 | Working AI capabilities | BLOCKED | docs/19-intelligence/rag-evaluation-results.md | e6aaad6711f03c8b319028dc1d420c61519d70e97f8a261f09427f411b807d28
R4 | Working AI capabilities | BLOCKED | docs/26-tevv/tevv-results.md | 5c67844f416dd5ef4b6292c7c85b0b7caa243ab02695b2b639494d74093f1060
R4 | Working AI capabilities | BLOCKED | docs/19-intelligence/intelligence-release-gate.md | 7abbf9dc972cf23a75f7c442c57ae3b4765f8673d7e70d0848a3650a961ebc7e
R4 | Evidence-driven delivery | MET | docs/18-delivery/definition-of-done.md | 7a6da85687556ed59c5eb3e1790b72699803b655d8ba5344c29a7d14c23d6d2c
R4 | Evidence-driven delivery | MET | docs/18-delivery/evidence-checklist.md | d8d08a5e1122269f622660b3111132bb21723fa7a66aff4b3ff4dc8e9e31c70a
R5 | Storytelling | MET | docs/42-executive/executive-narrative.md | 2b10115740e5c833ac1fb7c2c83b8c355517f577f2d8cd5df6f56f926ab8c90d
R5 | Storytelling | MET | docs/42-executive/problem-to-value-story.md | 553d4927a47b304bf6f76fd4aae9bb2ad51c22f1163a13417c90e49a0f6b9e22
R5 | Demo quality | PARTIAL | docs/42-executive/demo-day-script.md | 39b94b5382168d2e8d0150d1fc2b368f703c6534b30a9e0537604c839ff1cf2d
R5 | Explaining design choices | MET | docs/42-executive/architecture-defence.md | a6ece1c86ff07e36063b873251eba5fe3f53a8d25aa515226c47d88d8ce599dd
R5 | Explaining design choices | MET | docs/42-executive/ai-decision-defence.md | 0e8a5b6181762cfbee037b9105e0b10f9267f5d73d58f24c0603520f62e9aa0d
R5 | Trade-offs and limitations | MET | docs/final-prd/known-limitations.md | a40845b130c038d617aeaef6fb7c62172ec4159517967605adb198b5e105ab18
R5 | Trade-offs and limitations | MET | docs/42-executive/lessons-learned.md | 4724d80f8a8c7b2b674b70938c145f524317fc18f70bc70f608145496ad51c3f
R5 | Trade-offs and limitations | MET | docs/42-executive/residual-risks.md | 2dc0588056838f047b74c9026ed238f825059c9c3c9fd7a4ccad595cfe3557b2
R5 | Answering evaluator questions | MET | evidence/13-traceability/EVD-F-04-finding-coverage-matrix.csv | 055a52f15d9daafa8d76bc642da760ea3a404790ac7d0fcefbb9f76ba1016821
R5 | Answering evaluator questions | MET | evidence/13-traceability/EVD-F-04b-finding-disposition-final.csv | 24dc4df12754670d842a7f1d8fb2d8dfa03eb8214dd35758a7e26577a6e774d1
R5 | Answering evaluator questions | MET | evidence/EVIDENCE-INDEX.md | cd744fa5b570efad24d3b8a2b4165ae695516d4d9d1349631a544d9aba27d551

## Go-No-Go
Readiness gates G1 to G12
Source: docs/30-release/go-no-go-criteria.md (fixed before the decision) and docs/42-executive/production-readiness-decision.md; G1 and G9 updated to today. Pilot needs G1-G7; production needs G8-G12 as well.
Gate | Criterion | Mandatory for | State | Basis
G1 | Tests pass, coverage at or above floor | yes | PASS | 181 passed, 97% (apps and etl); CI green on 3.11 and 3.14
G2 | Evaluation at thresholds | yes | PASS (deterministic provider only) | 192 cases, 0 failures; real model untested
G3 | No original defect re-exploitable | yes | PASS | 0 of 12 attacks succeed
G4 | No known critical or high dependency vulnerability | yes | PASS | pip-audit: 0
G5 | Audit tamper-evident; reconstruction shown | yes | PASS (author-run) | EVD-N-02
G6 | Backup restore shown | yes | PASS (repository level) | EVD-N-03
G7 | Rollback defined and rehearsed | yes | PARTIAL | Defined; no cutover exists
G8 | Alerts routed to named humans | yes | FAIL | No collector, no recipients
G9 | Named approver and risk owners | yes | FAIL | Operator approves under provisional authority (OQ-05); 0 of 12 risk acceptances signed
G10 | Platform and identity provider exist | production | FAIL | Platform-neutral by decision (OQ-01); IdP deferred (OQ-07)
G11 | Independent evidence review | yes | FAIL | Builder and grader are the same agent
G12 | Compliance resolved | real data | FAIL | No regime named (OQ-04); candidate obligations unvalidated

## Decisions
23 open questions: the operator's decisions (Runbook 04)
Source: docs/44-decisions/open-questions-register-v2.md; record evidence/44-decisions/EVD-T-01-operator-decision-record.json. One person holds every role, so these are provisional.
Question | Subject | Status | Decision | What it means now
OQ-01 | Target platform | DECIDED | Stay platform-neutral. No cloud or runtime is named. | ADR-0009 stands: container image and compose file; IaC stays a non-provisioning stub (M-X2 stays NOT MET, accepted).
OQ-02 | Model A and Model B | DECIDED | No model is used. The deterministic provider stays the only provider. | R4 'Working AI capabilities' stays BLOCKED, now accepted by the operator. The Stage Q builder comparison (Sonnet vs Haiku, same vendor) stays the only portability evidence.
OQ-03 | Network egress | DECIDED | No network egress from the application. Build and demo run offline. | Matches what was built (offline demo, no model call).
OQ-04 | Regulatory obligations | DECIDED | No regime is named. The candidate obligations set stays an unvalidated working assumption. | `docs/25-governance/compliance-obligations.md` stays labelled candidate; RA-01 remains an unsigned risk acceptance.
OQ-05 | Stakeholders and approvers | DECIDED | The operator (Dinesh) approves everything as Transformation Lead, under provisional authority. No other named party exists. A CTO review stays recommended. | Gates stay self-signed and PROVISIONAL. This records the arrangement; it does not make the approvals independent. G9 and GOV-10 stay open.
OQ-06 | Operator portal in scope | RATIFIED | A thin read-only operations view, not an Angular portal. Previously RESOLVED (provisional). | B-7 resolved by decision.
OQ-07 | Identity provider | DEFERRED | No provider chosen. HS256 stays an interim scheme, not for production; JWKS stays a fail-closed stub. | Production identity remains an explicit gap (ADR-0004).
OQ-08 | Proxy KPIs acceptable | RATIFIED | The labelled proxy KPIs are accepted as the frozen baseline. No real business data exists. | Stage O comparison is valid only as proxies; the comparability caveat stays in the narrative.
OQ-09 | Financial data for ROI | DECIDED | No financial data. The benefit model stays in analyst-hours with sensitivity ranges and no money figure. | NPV -970 h expected, +5,525 h optimistic, -2,466 h downside stays the statement; verified benefit is nil.
OQ-10 | Evidence retention | RATIFIED | Evidence stays in the repository, hash-manifested and version-controlled. | Retention classes stay as written; there is no external append-only audit sink for runtime records.
OQ-11 | Authorisation to write | RATIFIED | The operator ratifies, in their own name, the write authorisation given as instruction D-009. A CTO ratification stays recommended. | EVD-G-04 stays unsigned as a document; this decision is recorded in EVD-T-01 and D-016.
OQ-12 | Time budget | DECIDED | Demo budget is 10 minutes plus 5 minutes of questions. No engagement deadline was stated. | The demo script stays at 10+5; the engagement deadline is UNKNOWN [UNK].
OQ-13 | Discovery folder collision | RATIFIED | The spine path `docs/00-preflight/discovery/` is authoritative. | D-001 stands.
OQ-14 | Data remediation location | RATIFIED | A derived curated layer; the fixture in `data/synthetic/` stays immutable. | ETL, quarantine and the original smoke assertions stand.
OQ-15 | REC-0001 collision intent | DECIDED | Handling decided: treat as a defect (lookup logic fixed, bad-key rows quarantined). The data owner's intent is UNKNOWN. | Implemented; 0 REC-0001 rows in the curated layer.
OQ-16 | Demo environment | DECIDED | Local, offline, deterministic provider. | Matches the rehearsed script. No recorded fallback video exists.
OQ-17 | Demo format and budget | DECIDED | 10 minutes plus 5 of questions, live and offline. This differs from the register default of 20 plus 10, and the difference is now a recorded decision. | Q-X5 stays PARTIAL: rehearsal was by the author only, no audience or recording.
OQ-18 | Agentic AI in scope | DECIDED | Not in scope. J6 stands as not-applicable. | B-12 closed by decision; the `ai_agent` persona stays a read-only suggester.
OQ-19 | Secret history disposition | DECIDED | Keep history unrewritten; treat the values as compromised; the repository is private. Nothing real exists to revoke: they are workshop placeholders, and none may be reused anywhere. | GOV-07 decided: private. The 10 history findings stay as recorded.
OQ-20 | Real deployment or readiness | DECIDED | Readiness decision only. Nothing is deployed. | The verdict NO-GO production on real data / CONDITIONAL GO controlled pilot on synthetic data stays the deliverable.
OQ-21 | Location data constraints | DECIDED | No limits stated. The minimisation default stays: location fields masked and excluded from prompts and from logs above INFO. | RA-10 (retention and rights undefined) stays an unsigned acceptance.
OQ-22 | Clean-repo contract retention | RATIFIED | The original sanity_check assertions stay unchanged. | H-X10 stands.
OQ-23 | Team size and skills | DECIDED | One operator plus the agent; sequential execution. | Stage ordering stays sequential; no parallel plan is needed.

## Risks
Residual risks (none accepted by a named person)
Source: docs/42-executive/residual-risks.md and docs/25-governance/risk-acceptance-register.md, with the Runbook 04 decisions applied. Owners are roles.
ID | Risk | Severity (agent view) | Owner role | Current position
RA-07 / DEBT-11 | Credential-shaped values remain in git history | High | Repository owner + Security | Repository private; values treated as compromised; history not rewritten (OQ-19)
RA-01 | Regulatory scope unresolved | High for real data | Sponsor + Compliance | No regime named (OQ-04); pilot on synthetic data only
RA-06 / TEVV-R-01 | Builder and grader are the same agent; no independent review | High | Release approver | Blocks an unconditional GO; ask 6 to the CTO
RA-02 | HS256 shared-secret identity; JWKS stub | High if networked | Security | Interim scheme kept (OQ-07 deferred)
RA-09 / TEVV-R-02 | Real model untested; thresholds valid only for the deterministic provider | High before a model | AI governance | No model by decision (OQ-02)
Stage Q | Model portability partly shown: safety yes, AI-output fidelity no | Medium | AI governance | 8 gaps specified in semantic layer v2.0; not re-tested
RA-04 / HC-R-01 | No four-eyes: requester can approve their own suggestion | Medium | Product | Before any action integration
RA-12 / DEBT-01 | Branch protection not enabled on main | Medium | Repository owner | GitHub reports the feature needs Pro for a private repository
DEBT-06 / F-48 | Terraform provisions nothing; image never built | Medium | Platform | Platform-neutral by decision (OQ-01)
N-R | No tracing; collector and alerts never run; no recipients | Medium | SRE | Before deployment
DEBT-04 | Audit sink is a local file; deletion of the tip cannot be prevented | Medium | Platform | Needs a platform
DEBT-08 / DEBT-09 | BR-04 violated by 354 of 354 rows; actual above declared weight on 171 rows | Medium | Business owner | Meaning unknown
F-42 | 1,992 of 3,000 historical events lack a usable correlation id | Low (history) | Data owner | New requests carry an id
Value | No business KPI measurable; NPV negative at fixture volume | Medium | Sponsor | Measure review time first
RA-03, 05, 08, 10, 11 | Purpose defaulting; approvals never expire; stale GPS undetectable; retention undefined; in-memory rate limit | Low to Medium | See risk-acceptance register

## Journey
Delivery journey: 20 stages in six phases
Stages A to R come from runbook/02-TRANSFORMATION-RUNBOOK.md; S and T are Runbooks 03 and 04. Evidence count = rows in the Evidence Register for that stage letter.
Stage | Phase | Stage name | Commit(s) | Evidence files
A | 1 Understand | Engagement mobilisation and read-only orientation | 698e858, f1b7809 | 15
B | 1 Understand | Qualification, stakeholders and problem framing | f1b7809 | 1
C | 1 Understand | Baseline: KPIs, current state, root cause, behaviour | 4c84af1 | 10
D | 2 Define | Semantic layer extraction | 4c84af1 | 9
E | 2 Define | Intervention qualification and initial PRD | 4c84af1 | 2
F | 2 Define | Target architecture, data and context, specs, traceability | 4c84af1 | 8
G | 2 Define | Transformation and migration planning | 4c84af1 | 3
H | 3 Build | Repo 2.0 modernisation and validation | 4c84af1 | 17
I | 3 Build | Implementation PRD and delivery planning | 4c84af1 | 0
J | 3 Build | Intelligence core, application, integration and agents | 4c84af1 | 9
K | 4 Prove | Human control, security, privacy, responsible AI, governance | 4c84af1 | 3
L | 4 Prove | TEVV and AI red teaming | 4c84af1 | 3
M | 4 Prove | Hardening, resilience, incident response, BC/DR | 4c84af1 | 15
N | 4 Prove | Release, observability, FinOps, vendor risk | 4c84af1 | 6
O | 5 Defend | Outcome measurement, value leakage, benefits | 4c84af1 | 2
P | 5 Defend | Operating model, handover, drift, scale, retirement | 4c84af1 | 3
Q | 5 Defend | Model portability validation and demonstration | 217afc5, e13758b, ab37ec8 | 25
R | 5 Defend | Executive defence, as-built PRD, production evidence pack | c7d94de, 96d5522 | 5
S | 6 Close-out | Rubric traceability (Runbook 03) | 1dcf6e8 | 9
T | 6 Close-out | Open questions and decisions (Runbook 04) | 1cde803 | 1
D (v2) | 6 Close-out | Semantic layer aligned to semantic-layer-build.txt | ad230eb | (in D)

## Semantic Layer
Semantic layer v2.0: files
The model-independent definition of the domain. Hashes recorded in evidence/11-data-context/EVD-D-06-semantic-layer-v2-hashes.json.
File | Format and role | Bytes | Link
semantic-layer/README.md | Markdown: for people | 3526 | open
semantic-layer/SEMANTIC-COMPLETENESS.md | Markdown: for people | 5219 | open
semantic-layer/access-semantics.yaml | YAML: definition | 7756 | open
semantic-layer/ai-context-policy.yaml | YAML: definition | 1568 | open
semantic-layer/api-contract.json | JSON / JSON Schema | 3494 | open
semantic-layer/business-rules.yaml | YAML: definition | 5598 | open
semantic-layer/domain-knowledge.md | Markdown: for people | 3795 | open
semantic-layer/entities.yaml | YAML: definition | 23145 | open
semantic-layer/enum-violations.md | Markdown: for people | 6272 | open
semantic-layer/generate.py | Generator or test | 1071 | open
semantic-layer/generated/semantic-layer.json | JSON / JSON Schema | 66333 | open
semantic-layer/glossary.md | Markdown: for people | 7284 | open
semantic-layer/metrics.yaml | YAML: definition | 2622 | open
semantic-layer/relationships.yaml | YAML: definition | 1249 | open
semantic-layer/schemas/semantic-layer.schema.json | JSON / JSON Schema | 6215 | open
semantic-layer/status-taxonomy.yaml | YAML: definition | 2088 | open
semantic-layer/tests/__init__.py | Generator or test | 0 | open
semantic-layer/tests/rule_eval.py | Generator or test | 2225 | open
semantic-layer/tests/test_semantic_layer.py | Generator or test | 6856 | open
semantic-layer/workflow-semantics.yaml | YAML: definition | 6597 | open